## Projects
Fiscal Year | Fund No. | Fund Name | Program | Account # | Program Name | Project Name | Current Phase | Overall Budget | Construction PO #s | Design Engineer | Professional Service Agreement (PSA) Amount | Actual PSA Spent | Fiscal Year Design Complete | Fiscal Year Bid | Construction Start Date | Construction Completion Date | Fiscal Year Construction Completed | Planned Construction Completion Date | Inspector | COA Project Engineer | Contractor | Additional Funding | MPO STBG Funds | Engineer's Est | Bid Amount | Construction Change Orders | Anticipated Costs Unincombered | Final Construction Costs | Estimated COA Engineering / Admin | Actual COA Engineering / Admin | Total Anticipated Costs (PSA+Est+COA Est) | Actual Contractual Costs + Estimated COA | Remaining Budget (Budget-Total Antic.) | NPDES Permit | Available Balance (11/04/2025) | RFP | Distinct Count
2017/18 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | Siphon Rehab (7 locations) | Complete |  | 58661 | WHKS | 86700 |  | 2019/20 | 2020/21 | 2020-12-22 | 2022-02-01 | 2021/22 | 2021-12-31 | WHKS | Hafiz | Visu-Sewer | No | No | 900000 | 1440778 |  |  | 1409307.8 |  |  | 986700 | 1496007.8 | -986700 | No |  | No | 1
2018/19 | 560 | Stormwater Utility | Stormwater | 560-8635-489 | Stormwater Erosion Control Program | South Skunk River (various locations between South East 16th Street and East Lincoln Way) | Design | 654000 | [22 empty] | 0 | 0 | 654000 |  | 628400 | Yes | 1
2018/19 | 560 | Stormwater Utility | Stormwater | 560-8657-489 | Low Point Drainage Improvements | Airport Rd (from University Blvd to S. Riverside Dr.) | Complete | 195970 | 63108 | WHKS | 0 | 0 | 2023/24 | 2023/24 | 2024-05-15 | 2024-11-30 | 2024/25 | 2025-08-01 | Scott S | Hafiz | All Star Concrete | No | No | 182110.5 | 194388.1 |  |  | 160643 |  |  | 182110.5 | 160643 | 13859.5 | No | 0 | No | 1
2019/20 | 380 | 2019/20 GO Bonds | Street Improvements | 380-8165-439 | Concrete Pavement Improvements | Center Ave (from Lincoln Way to E 2nd St) Des Moines Ave (from Lincoln Way to E 3rd St) Douglas Ave (from 7th to 10th) E 2nd Street (from Duff Ave. to Center Ave) E 3rd Street (from Duff Ave to E. of Des Moines St) | Complete |  | 59264 | Tracy | 0 |  | 2020/21 | 2020/21 | 2021-05-01 | 2023-01-26 | 2022/23 | 11/'19/2021 | Jared | Hafiz | Manatt's | No | No | 2203927.03 | 1571889.4 |  |  | 1583919.49 |  |  | 2203927.03 | 1583919.49 | -2203927.03 | No | 0 | No | 1
2019/20 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | Basin 10 (Clark Ave to Maxwell Ave) | Complete |  | 57882 58953 | WHKS | 75000 |  | 2020/21 | 2020/21 | 2022-05-01 | 2023-01-18 | 2022/23 | 2023-01-18 | WHKS | Hafiz | Municipal Tool | No | No | 1935315 | 1283163.75 |  |  | 814323.71 |  |  | 2010315 | 889323.71 | -2010315 | No |  | No | 1
2019/20 | 560 | Stormwater Utility | Stormwater | 560-8636-489 | Stormwater Erosion Control Program | Ioway Creek (6th St. to 13th St) | Construction | 1258000 | 64278 | WHKS | 126320 |  | 2024/25 | 2024/25 | 2025-06-16 |  | 2025/26 | 2025-12-31 | Jake/Jared | Liz | Iowa Earth Works |  | No | 958953 | 787433 |  |  |  | 123680 |  | 1208953 | 250000 | 49047 | Yes | 196926 | No | 0
2019/20 | 561 | Stormwater Improvements | Stormwater | 561-8636-489 | Stormwater Erosion Control Program | Ioway Creek (6th St. to 13th St) | Construction | 900000 | 64278 | WHKS | 0 | 0 | 2024/25 | 2024/25 | 2025-06-16 |  | 2025/26 | 2025-12-31 | Jake/Jared | Liz | Iowa Earth Works |  | No | 900000 | 900000 | 0 | 0 | 900000 | 0 | 0 | 900000 | 900000 | 0 |  | 0 | No | 1
2020/21 | 122 | American Rescue Plan | Sanitary Sewer System | 122-8460-489 | Prairie View Utility Extension | East Lincoln Way (Freel to Teller) | Complete |  | 59817 | Stanley Consultants | 0 | 0 | 2020/21 | 2020/21 | 2021-11-01 | 2023-06-01 | 2024/25 | 2023-06-01 | Jesus | Dean | Keller | EDA | No | 2691023.83 | 2988836 |  |  | 1225735 |  |  | 2691023.83 | 1225735 | -2691023.83 | Yes | 0 | Yes | 1
2020/21 | 122 | American Rescue Plan | Sanitary Sewer System | 122-8519-489 | Prairie View Utility Extension | East Lincoln Way (Freel to Teller) | Complete | 86751 | 59817 | Stanley Consultants | 0 | 0 | 2020/21 | 2020/21 | 2021-11-01 | 2023-06-01 | 2024/25 | 2023-06-01 | Jesus | Dean | Keller | EDA | No | 215635.86 | 239500 |  |  | 1944800.74 |  |  | 215635.86 | 1944800.74 | -128884.86 | Yes | -273593 | Yes | 0
2020/21 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | E 13th Street (Duff Ave to Meadowlane Ave) | Complete | 555000 | 59602 | WHKS | 27198.332 | 27150.96 | 2020/21 | 2021/22 | 2022-04-01 | 2025-07-30 | 2025/26 | 2023-05-02 | Scott M | Dean | Con-Struct | Yes | No | 382707 | 555000 |  |  | 663481.45 |  |  | 409905.332 | 690679.782 | 145094.668 | No |  | No | 0
2020/21 | 381 | 2020/21 GO Bonds | Street Improvements | 381-8141-439 | Arterial Street Pavement Improvements | E 13th Street (Duff Ave to Meadowlane Ave) | Complete | 900000 | 59602 | WHKS | 25728.696 | 25683.8837 | 2020/21 | 2021/22 | 2022-04-01 | 2025-07-30 | 2025/26 | 2023-05-02 | Scott M | Dean | Con-Struct | Yes | No | 536955.1 | 525000 |  |  | 525000 |  |  | 562683.796 | 550728.696 | 337316.204 | No |  | No | 0
2020/21 | 320 | Street Construction | Street Improvements | 320-8141-439 | Arterial Street Pavement Improvements | E 13th Street (Duff Ave to Meadowlane Ave) | Complete | 1600000 | 59602 | WHKS | 78411.264 | 78274.6932 | 2020/21 | 2021/22 | 2022-04-01 | 2025-07-30 | 2025/26 | 2023-05-02 | Scott M | Dean | Con-Struct | Yes | No | 1757735.6 | 1600000 | -55427.87 |  | 1486168.58 | 476134.97 |  | 2312281.834 | 2040714.814 | -712281.834 | No |  | No | 1
2020/21 | 381 | 2020/21 GO Bonds | Street Improvements | 381-8166-439 | Concrete Pavement Improvements | Ford St (Dayton Ave to Bell Ave) Bell Ave (E Lincoln Way to Ford Street) S. 17th St (West of Golden Aspen Dr to S. Kellogg Ave.) South Kellogg Ave ( S. 17th to S. 16th St) | Complete |  | 60631 | Tracy | 0 | 0 | 2021/22 | 2021/22 | 2023-04-01 | 2024-05-01 | 2023/24 | 2022-12-31 | Scott M | Hafiz | Con-Struct | No | No | 666563 | 666666 |  |  | 664014 |  |  | 666563 | 664014 | -666563 | No | 0 | No | 1
2020/21 | 381 | 2020/21 GO Bonds | Street Improvements | 381-8166-439 | Concrete Pavement Improvements | 8th St (Northwestern Ave to Duff Ave) | Complete | 1581905.25 | 59263 | Tracy | 0 | 0 | 2020/21 | 2020/21 | 2021-06-01 | 2022-02-10 | 2021/22 | 6/31/22 |  | Hafiz | Manatt's | No | No | 1581905.25 | 1156246.21 |  |  | 1173433.56 |  |  | 1581905.25 | 1173433.56 | 0 | No | 0 | No | 1
2020/21 | 60 | Road Use Tax | Street Improvements | 060-8023-431 | Collector Street Pavement Improvements | E 20th Street (Duff Ave to Meadowlane Ave) | Complete | 776718.91 |  | Dean | 0 | 0 | 2020/21 | 2021/22 | 2021-09-01 | 2022-08-09 | 2022/23 | 2022-08-09 | Scott S | Dean | All Star Concrete | No | No | 901527.95 | 776718.91 |  |  | 743263.53 |  |  | 901527.95 | 743263.53 | -124809.04 | No | 0 | No | 1
2020/21 | 60 | Road Use Tax | Street Improvements | 060-8166-439 | Concrete Pavement Improvements | 8th St (Northwestern Ave to Duff Ave) | Complete | 100000 | 59263 | Tracy | 0 | 0 | 2020/21 | 2020/21 | 2021-06-01 | 2022-02-10 | 2021/22 | 6/31/22 |  | Hafiz | Manatt's | No | No | 100000 | 100000 |  |  | 111094.7 |  |  | 100000 | 111094.7 | 0 | No | 0 | No | 0
2020/21 | 87 | CDBG | Community Block Grant | 087-0690-464 | CDBG Improvements (Baker Subdivision) | Baker Street | Complete |  | 58517 | CDA |  |  | 2020/21 | 2020/21 | 2020-11-01 | 2022-08-31 | 2022/23 | 2021-06-30 | Scott S | Tracy | Con-Struct | CDBG | No | 1402922 | 1317872.65 |  |  | 1401355.78 |  |  | 1402922 | 1401355.78 | -1402922 | Yes | 0 | No | 1
2020/21 | 510 | Water Utility | Water Distribution | 510-8430-489 | Water System Improvements | East Lincoln Way (Freel to Teller) | Complete | 72355 | 59817 | Stanley Consultants | 47210 |  | 2020/21 | 2020/21 | 2021-11-01 | 2023-08-31 | 2023/24 | 2023-06-01 | Jesus | Dean | Keller | EDA | No | 452460 | 644997.5 |  |  | 786308.31 |  |  | 499670 | 833518.31 | -427315 | Yes |  | Yes | 0
2020/21 | 520 | Sewer Utility | Sanitary Sewer System | 520-8519-489 | Sanitary Sewer System Improvements | East Lincoln Way (Freel to Teller) | Complete | 316392 | 59817 | Stanley Consultants | 206860 |  | 2020/21 | 2020/21 | 2021-11-01 | 2023-06-01 | 2024/25 | 2023-06-01 | Jesus | Dean | Keller | EDA | No | 1250735.32 | 1389152.6 |  |  | 4461037.25 | 697193.13 |  | 2154788.45 | 5365090.38 | -1838396.45 | Yes | 0 | Yes | 0
2020/21 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | E 13th Street (Duff Ave to Meadowlane Ave) | Complete | 45000 | 59602 | WHKS | 25728.696 | 25683.8837 | 2020/21 | 2020/21 | 2022-04-01 | 2025-07-30 | 2025/26 | 2023-05-02 | Scott M | Dean | Con-Struct | Yes | No | 41300 | 45000 |  |  | 40000 |  |  | 67028.696 | 65728.696 | -22028.696 | No | -498 | No | 0
2020/21 | 560 | Stormwater Utility | Stormwater | 560-8642-489 | Stormwater Improvement Program | E 13th Street (Duff Ave to Meadowlane Ave) | Complete | 255000 | 59602 | WHKS | 10257.254 | 10239.3887 | 2020/21 | 2021/22 | 2022-04-01 | 2025-07-30 | 2025/26 | 2023-05-02 | Scott M | Dean | Con-Struct | Yes | No | 261302.3 | 209292.9 |  |  | 164215 |  |  | 271559.554 | 174472.254 | -16559.554 | No | 0 | No | 0
2021/22 | 382 | 2021/22 GO Bonds | Street Improvements | 382-8167-439 | Concrete Pavement Improvements | 24th St (PineHurst Dr to Hayes Ave) Stange Ave (Blankenburg Dr. to 24th St.) | Complete | 3100000 | 61756 | HR Green | 233400 | 289415 | 2021/22 | 2021/22 | 2024-04-10 | 2025-01-15 | 2024/25 | 2025-01-31 | Scott S | Dean | Con-Struct | Yes | Yes | 2552314.23 | 2392583.23 |  |  | 2454270.63 | 140000 |  | 2925714.23 | 2827670.63 | 174285.77 | Yes | 0 | Yes | 0
2021/22 | 30 | Local Option Sales Tax | Street Improvements | 030-8167-439 | Concrete Pavement Improvements | 24th St (PineHurst Dr to Hayes Ave) Stange Ave (Blankenburg Dr. to 24th St.) | Complete | 80000 | 61756 | HR Green | 0 | 0 | 2021/22 | 2021/22 | 2024-04-10 | 2025-01-15 | 2024/25 | 2025-01-31 | Scott S | Dean | Con-Struct | Yes | Yes | 80000 | 80000 |  |  | 80000 |  |  | 80000 | 80000 | 0 | Yes | 0 | Yes | 1
2021/22 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | US Hwy 69 Grand Ave (6th St to 12th St) Murray Dr (1400 block) SE 2nd St (S Duff-Sumner) 11th St (Grand - 150' east) | Complete |  | 61160 | Cesar | 0 | 0 | 2022/23 | 2022/23 | 2023-04-01 | 2024-02-28 | 2023/24 | 2024-06-01 | Scott M | Cesar | Synergy | No | No | 2001096 | 2286813 |  |  | 2347765.51 |  |  | 2001096 | 2347765.51 | -2001096 | No |  | No | 1
2021/22 | 380 | 2019/20 GO Bonds | Street Improvements | 380-8181-439 | S. 16th & S. Duff Improvements | S. 16th (S Grand Ave to East of S Duff Ave) | Complete |  | 60632 | Shive Hattery |  |  | 2021/22 | 2021/22 | 2022-08-01 | 2024-06-12 | 2023/24 | 2023-12-31 | Jesus | Hafiz | Con-Struct | Yes | No | 2312761.3 | 2217358.6 |  |  | 3229306.66 |  |  | 2312761.3 | 3229306.66 | -2312761.3 | No |  | No | 0
2021/22 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | Stafford Ave (13th St to Carroll Ave.) | Complete | 500000 | 60633 | Tracy | 0 | 0 | 2022/23 | 2022/23 | 2022-07-01 | 2022-12-30 | 2022/23 | 2022-12-30 | Jesus | Hafiz | Manatt's | No | No | 425400 | 404802.2 |  |  | 388536.86 |  |  | 425400 | 388536.86 | 74600 | No |  | No | 0
2021/22 | 320 | Street Construction | Street Improvements | 320-8167-439 | Concrete Pavement Improvements | 24th St (PineHurst Dr to Hayes Ave) Stange Ave (Blankenburg Dr. to 24th St.) | Complete | 1600000 | 61756 | HR Green | 0 |  | 2021/22 | 2021/22 | 2024-04-10 | 2025-01-15 | 2024/25 | 2025-01-31 | Scott S | Dean | Con-Struct | Yes | Yes | 1600000 | 1600000 |  |  | 1600000 |  |  | 1600000 | 1600000 | 0 | Yes | 0 | Yes | 0
2021/22 | 30 | Local Option Sales Tax | Shared Use Paths | 030-8811-439 | Shared Use Path Maintenance | S. 16th (S Grand Ave to East of S Duff Ave) | Complete |  | 60632 | Shive Hattery |  |  | 2021/22 | 2021/22 | 2022-08-01 | 2024-06-12 | 2023/24 | 2023-12-31 | Jesus | Hafiz | Con-Struct | Yes | No | 0 | 28600 |  |  | 28600 |  |  | 0 | 28600 | 0 | No |  | No | 0
2021/22 | 320 | Street Construction | Street Improvements | 320-8181-439 | S. 16th & S. Duff Improvements | S. 16th (S Grand Ave to East of S Duff Ave) | Complete |  | 60632 | Shive Hattery |  |  | 2021/22 | 2021/22 | 2022-08-01 | 2024-06-12 | 2023/24 | 2023-12-31 | Jesus | Hafiz | Con-Struct | Yes | No | 414953 | 442450.6 |  |  | 188372.75 |  |  | 414953 | 188372.75 | -414953 | No |  | No | 1
2021/22 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | S. 16th (S Grand Ave to East of S Duff Ave) | Complete |  | 60632 | Shive Hattery |  |  | 2021/22 | 2021/22 | 2022-08-01 | 2024-06-12 | 2023/24 | 2023-12-31 | Jesus | Hafiz | Con-Struct | Yes | No | 114000 | 166240 |  |  | 165000 |  |  | 114000 | 165000 | -114000 | No |  | No | 0
2021/22 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | S Duff Ave (5th St. to Lincoln Way) | Complete |  | 61160 | Cesar | 0 | 0 | 2022/23 | 2022/23 | 2023-04-01 | 2024-02-28 | 2023/24 | 2023-12-31 | Scott Miller | Cesar | Synergy | No | No | 2001096 | 2286813.8 |  |  | 2347765.51 |  |  | 2001096 | 2347765.51 | -2001096 | No | 0 | No | 1
2021/22 | 382 | 2021/22 GO Bonds | Street Improvements | 382-8101-439 | Seal Coat Street Pavement Improvements | Stafford Ave (13th St to Carroll Ave.) | Complete | 750000 | 60633 | Tracy | 0 | 0 | 2021/22 | 2021/22 | 2022-07-01 | 2022-12-30 | 2022/23 | 2022-12-30 | Jesus | Hafiz | Manatt's | No | No | 600922.5 | 585982.94 |  |  | 591963.48 |  |  | 600922.5 | 591963.48 | 149077.5 | No |  | No | 1
2021/22 | 382 | 2021/22 GO Bonds | Street Improvements | 382-8130-439 | Collector Street Pavement Improvements | Hoover Ave (24th St to Top-O-Hollow) | Complete |  | 60574 | Dean | 0 | 0 | 2021/22 | 2021/22 | 2022-07-01 | 2023-10-03 | 2023/24 | 2023-12-31 | Jesus | Dean | Manatt's | No | No | 1916748.18 | 2057300.43 |  |  | 2163578.36 |  |  | 1916748.18 | 2163578.36 | -1916748.18 | No |  | No | 0
2021/22 | 320 | Street Construction | Street Improvements | 320-8142-439 | Arterial Street Pavement Improvements | North Dakota Ave (from Ontario to UPRR) Ontario St (from North Dakota to Woodstock) | Complete |  | 60733 | MSA | 51682.7408 | 51682.7408 | 2021/22 | 2021/22 | 2022-07-01 | 2023-04-17 | 2022/23 | 2022-12-31 | Jared | Hafiz | Con-Struct | Yes | No | 755850.4826 | 899999.3771 |  |  | 898661.51 |  |  | 807533.2233 | 950344.2507 | -807533.2233 | No |  | No | 1
2021/22 | 382 | 2021/22 GO Bonds | Street Improvements | 382-8142-439 | Arterial Street Pavement Improvements | North Dakota Ave (from Ontario to UPRR) Ontario St (from North Dakota to Woodstock) | Complete |  | 60733 | MSA | 30442.2592 | 30442.2592 | 2021/22 | 2021/22 | 2022-07-01 | 2023-04-17 | 2022/23 | 2022-12-31 | Jared | Hafiz | Con-Struct | Yes | No | 446451.8102 | 530119.2229 |  |  | 529331.19 |  |  | 476894.0695 | 559773.4493 | -476894.0695 | No |  | No | 0
2021/22 | 382 | 2021/22 GO Bonds | Street Improvements | 382-8153-439 | Downtown Street Improvements | Alley (Duff Ave. to Sherman Ave.) | Complete | 245000 | 60316 | Dean | 0 | 0 | 2021/22 | 2021/22 | 2022-08-01 | 2022-10-18 | 2022/23 | 2022-12-31 | Scott S | Dean | Con-Struct | No | No | 134136.25 | 127952 |  |  | 128224.62 |  |  | 134136.25 | 128224.62 | 110863.75 | No |  | No | 1
2021/22 | 510 | Water Utility | Water Distribution | 510-8461-481 | Water System Improvements | North 2nd St (N Elm Ave to N Maple Ave) South Kellogg Ave (South to Carroll Ave) | Complete | 75000 | 61047 | Dean | 0 | 0 | 2021/22 | 2021/22 | 2022-09-01 | 2022-12-31 | 2022/23 | 2022-12-31 | Jared | Dean | All Star Concrete | No | No | 70690 | 74258 |  |  | 83085.5 |  |  | 70690 | 83085.5 | 4310 | No |  | No | 1
2021/22 | 382 | 2021/22 GO Bonds | Street Improvements | 382-8155-439 | Asphalt Street Pavement Improvements | Harcourt Dr (from Garnet Dr to Jewel Dr) Opal Circle (from Opal Dr to east end) Opal Dr (Jewel Dr to Crystal St) Top-O-Hollow Rd (Bloomington Rd to Dawes Dr.) Turquoise Circle (Onyx St to S. End) | Complete |  | 60457 | Tracy | 0 | 0 | 2021/22 | 2021/22 | 2022-04-18 | 2022-11-18 | 2022/23 | 2022-12-31 | Scott S | Hafiz | Manatt's | No | No | 1900297.52 | 2118380.02 |  |  | 1989436.7073 |  |  | 1900297.52 | 1989436.7073 | -1900297.52 | No |  | No | 0
2021/22 | 382 | 2021/22 GO Bonds | Street Improvements | 382-8167-439 | Concrete Pavement Improvements | North 2nd St (N Elm Ave to N Maple Ave) South Kellogg Ave (South to Carroll Ave) | Complete | 900000 | 61047 | Dean | 0 | 0 | 2021/22 | 2021/22 | 2022-09-01 | 2022-12-31 | 2022/23 | 2022-12-31 | Jared | Dean | All Star Concrete | No | No | 622216.41 | 872793 |  |  | 776510.98 |  |  | 622216.41 | 776510.98 | 277783.59 | No |  | No | 0
2021/22 | 30 | Local Option Sales Tax | Street Improvements | 030-8115-439 | Asphalt Street Pavement Improvements | Harcourt Dr (from Garnet Dr to Jewel Dr) Opal Circle (from Opal Dr to east end) Opal Dr (Jewel Dr to Crystal St) Top-O-Hollow Rd (Bloomington Rd to Dawes Dr.) Turquoise Circle (Onyx St to S. End) | Complete |  | 60457 | Tracy | 0 | 0 | 2021/22 | 2021/22 | 2022-04-18 | 2022-11-18 | 2022/23 | 2022-12-31 | Scott S | Hafiz | Manatt's | No | No | 15000 | 15000 |  |  | 15000 |  |  | 15000 | 15000 | -15000 | No |  | No | 1
2021/22 | 560 | Stormwater Utility | Stormwater | 560-8601-489 | Stormwater Quality Improvements | 24th St (PineHurst Dr to Hayes Ave) Stange Ave (Blankenburg Dr. to 24th St.) | Complete | 100000 | 61756 | HR Green |  |  | 2021/22 | 2021/22 | 2024-04-10 | 2025-01-15 | 2024/25 | 2025-01-31 | Scott S | Dean | Con-Struct | Yes | Yes | 100000 | [6 empty] | 100000 | 0 | 0 | Yes | 73360 | Yes | 0
2021/22 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | Stafford Ave (13th St to Carroll Ave.) | Complete | 10000 | 60633 | Tracy | 0 | 0 | 2022/23 | 2022/23 | 2022-07-01 | 2022-12-30 | 2022/23 | 2022-12-30 | Jesus | Hafiz | Manatt's | No | No | 0 | 0 |  |  | 8489.8 |  |  | 0 | 8489.8 | 10000 | No |  | No | 0
2021/22 | 560 | Stormwater Utility | Stormwater | 560-8624-489 | Stormwater Improvement Program | Hoover Ave (24th St to Top-O-Hollow) | Complete |  | 60574 | Dean | 0 | 0 | 2021/22 | 2021/22 | 2022-07-01 | 2023-10-03 | 2023/24 | 2023-12-31 | Jesus | Dean | Manatt's | No | No | 121486 | 128187.15 |  |  | 133556.85 |  |  | 121486 | 133556.85 | -121486 | No | 0 | No | 1
2021/22 | 560 | Stormwater Utility | Stormwater | 560-8626-489 | Stormwater Detention/Retention Maintenance Program | Northridge Heights Pond on GW Carver | Close-Out | 130091 | 63112 | CGA | 25200 | 24908.3 | 2023/24 | 2023/24 | 2024-10-01 |  | 2024/25 | 2024-12-01 | Jake | Hafiz | Tallgrass Land Stewardship Co. | No | No | 84980 | 111600 | 4650 | 35000 |  | 35000 |  | 145180 | 60200 | -50089 | No | 2380 | No | 1
2021/22 | 560 | Stormwater Utility | Stormwater | 560-8637-489 | Stormwater Erosion Control Program | Bloomington Waterway (Hyde Ave to Harrison Road) | Complete | 350000 | 63043 | Bolton & Menk | 52000 | 52000 | 2023/24 | 2021/22 | 2024-05-01 | 2024-12-01 | 2023/24 | 2024-12-31 | Jake | Liz | Con-Struct | No | No | 271910 | 206340 |  |  | 176305.2 | 20000 |  | 343910 | 248305.2 | 6090 | No | 0 | No | 1
2021/22 | 520 | Sewer Utility | Sanitary Sewer System | 520-8572-489 | Sanitary Sewer System Improvements | North 2nd St (N Elm Ave to N Maple Ave) South Kellogg Ave (South to Carroll Ave) | Complete | 65000 | 61047 | Dean | 0 | 0 | 2021/22 | 2021/22 | 2022-09-01 | 2022-12-31 | 2022/23 | 2022-12-31 | Jared | Dean | All Star Concrete | No | No | 64335 | 48727.8 |  |  | 14445 |  |  | 64335 | 14445 | 665 | No |  | No | 0
2021/22 | 560 | Stormwater Utility | Stormwater | 560-8642-489 | Stormwater Improvement Program | 24th St (PineHurst Dr to Hayes Ave) Stange Ave (Blankenburg Dr. to 24th St.) | Complete | 200000 | 61756 | HR Green | 0 | 0 | 2021/22 | 2021/22 | 2024-04-10 | 2025-01-15 | 2024/25 | 2025-01-31 | Scott S | Dean | Con-Struct | Yes | Yes | 100000 | 179731 |  |  | 120270.2 |  |  | 100000 | 120270.2 | 100000 | Yes | 0 | Yes | 0
2021/22 | 560 | Stormwater Utility | Stormwater | 560-8642-489 | Stormwater Improvement Program | S. 16th (S Grand Ave to East of S Duff Ave) | Complete |  | 60632 | Shive Hattery |  |  | 2021/22 | 2021/22 | 2022-08-01 | 2024-06-12 | 2023/24 | 2023-12-31 | Jesus | Hafiz | Con-Struct | Yes | No | 1028681.5 | 1259781.6 |  |  | 200000 |  |  | 1028681.5 | 200000 | -1028681.5 | No | 0 | No | 0
2021/22 | 522 | Sewer Improvements (SRF) | Sanitary Sewer System | 522-8549-489 | Sanitary Sewer System Improvements | Worrell Creek Trunk Line | Will not proceed | 1158946 |  | WHKS | 191000 | 90908.15 | 2024/25 | 2024/25 |  |  | 2025/26 | 2025-12-31 | WHKS | Hafiz |  | No | No | [7 empty] | 191000 | 191000 | 967946 | No |  | No | 1
2021/22 | 522 | Sewer Improvements (SRF) | Sanitary Sewer System | 522-8550-489 | Sanitary Sewer System Improvements | Ames High School & Veenker Golf | Complete | 3922000 | 61570 | WHKS | 251000 | 162169.04 | 2022/23 | 2022/23 | 2023-10-01 | 2024-12-31 | 2024/25 | 2024-06-01 | WHKS | Hafiz | Municipal Tool | No | No | 2140000 | 3791558.69 |  |  | 3472507.52 | 37830.96 |  | 2428830.96 | 3761338.48 | 1493169.04 | No | 0 | No | 1
2022/23 | 122 | American Rescue Plan | Sanitary Sewer System | 122-8571-489 | Ames Plan 2040 Sanitary | N Sunset Ridge Sanitary Sewer | Complete | 336319.5 | 60633 | Bolton & Menk |  |  | 2022/23 | 2022/23 | 2023-03-01 | 2024-12-17 | 2023/24 | 2023/24 | Jesus | Cesar | Rognes Corp | No | No | 274287.24 | 338776.02 |  |  | 336319.5 |  |  | 274287.24 | 336319.5 | 62032.26 | No | 0 | No | 0
2022/23 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | 9th St (Brookridge Ave to Northwestern Ave) Brookridge Ave (6th St to Ridgewood Ave) Alley (6th St to 9th St) Lee St (Brookridge Ave to Ridgewood Ave) Ridgewood Ave (6th St to 9th St) | Complete | 450000 | 62065 | WHKS | 0 | 0 | 2022/23 | 2022/23 | 2023-04-25 |  | 2025/26 | 2024-12-31 | Jared | Hafiz | Shekar | No | No | 648270 | 450000 |  |  | 304719.63 |  |  | 648270 | 304719.63 | -198270 | No |  | No | 0
2022/23 | 383 | 2022/23 GO Bonds | Street Improvements | 383-8168-439 | Concrete Pavement Improvements | 9th St (Brookridge Ave to Northwestern Ave) Brookridge Ave (6th St to Ridgewood Ave) Alley (6th St to 9th St) Lee St (Brookridge Ave to Ridgewood Ave) Ridgewood Ave (6th St to 9th St) | Complete | 3600000 | 62065 | WHKS | 312400 | 312400 | 2022/23 | 2022/23 | 2023-04-25 |  | 2025/26 | 2024-12-31 | Jared | Hafiz | Shekar | No | No | 2466848.75 | 2753260.58 |  |  | 2162800.5 | 200000 | 200000 | 2979248.75 | 2675200.5 | 620751.25 | No | 266727 | No | 0
2022/23 | 383 | 2022/23 GO Bonds | Alley Pavement Improvements | 383-8170-439 | Concrete Pavement Improvements | 9th St (Brookridge Ave to Northwestern Ave) Brookridge Ave (6th St to Ridgewood Ave) Alley (6th St to 9th St) Lee St (Brookridge Ave to Ridgewood Ave) Ridgewood Ave (6th St to 9th St) | Complete | 400000 | 62065 | WHKS | 0 | 0 | 2022/23 | 2022/23 | 2023-04-25 |  | 2025/26 | 2024-12-31 | Jared | Hafiz | Shekar | No | No | 400000 | 400000 |  |  | 400000 | 0 |  | 400000 | 400000 | 0 | No | -6978 | No | 0
2022/23 | 30 | Local Option Sales Tax | Shared Use Paths | 030-8116-439 | Asphalt Street Pavement Improvements | Oakwood Rd (State Ave to University Ave) | Complete | 32000 | 62021 | WHKS | 0 | 0 | 2022/23 | 2023/24 | 2024-07-06 | 2024-08-01 | 2024/25 | 2024-07-01 | Jesus | Dean | Con-Struct | No | No | 33913.4214 | 30522.0793 |  |  | 33094.3738 |  |  | 33913.4214 | 33094.3738 | -1913.4214 | No |  | No | 0
2022/23 | 60 | Road Use Tax | Street Improvements | 060-8166-439-7517 | Asphalt Street Pavement Improvements | Oakwood Rd (State Ave to University Ave) | Complete | 38000 | 62021 | WHKS | 0 | 0 | 2022/23 | 2023/24 | 2024-07-06 | 2024-08-01 | 2024/25 | 2024-07-01 | Jesus | Dean | Con-Struct | No | No | 39861.5786 | 35875.4207 |  |  | 38898.8762 |  |  | 39861.5786 | 38898.8762 | -1861.5786 | No |  | No | 0
2022/23 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | Oakwood Rd (State Ave to University Ave) | Complete |  | 62021 | WHKS | 0 | 0 | 2022/23 | 2023/24 | 2024-07-06 | 2024-08-01 | 2024/25 | 2024-07-01 | Jesus | Dean | Con-Struct | No | No | 0 | 0 |  |  | 27090 |  |  | 0 | 27090 | 0 | No |  | No | 0
2022/23 | 60 | Road Use Tax | Street Improvements | 060-7770-439 | Neighborhood Curb Replacement Program | Murray Dr (Northwestern to Grand Ave) | Complete | 300000 | 61683 | Hafiz | 0 | 0 | 2021/22 | 2022/23 | 2023-05-01 | 2024-01-10 | 2023/24 | 2024-01-31 | Jared | Hafiz | Manatt's | No | No | 300000 | 300000 |  |  | 300000 |  |  | 300000 | 300000 | 0 | No |  | No | 1
2022/23 | 384 | 2023/24 GO Bonds | Street Improvements | 384-8171-439 | Concrete Pavement Improvements | 9th St (Brookridge Ave to Northwestern Ave) Brookridge Ave (6th St to Ridgewood Ave) Alley (6th St to 9th St) Lee St (Brookridge Ave to Ridgewood Ave) Ridgewood Ave (6th St to 9th St) | Complete | 400000 | 62065 | WHKS | 0 | 0 | 2022/23 | 2022/23 | 2023-04-25 |  | 2025/26 | 2024-12-31 | Jared | Hafiz | Shekar | No | No | 400000 | 400000 |  |  | 400000 |  |  | 400000 | 400000 | 0 | No | -6978 | No | 0
2022/23 | 510 | Water Utility | Street Improvements | 510-8194-439 | Right-of-Way Restoration | 9th St (Brookridge Ave to Northwestern Ave) Brookridge Ave (6th St to Ridgewood Ave) Alley (6th St to 9th St) Lee St (Brookridge Ave to Ridgewood Ave) Ridgewood Ave (6th St to 9th St) | Complete |  | 60913 |  | 0 | 0 | 2022/23 | 2022/23 | 2023-04-25 |  | 2025/26 | 2024-12-31 | Jake | Hafiz | Country Landscapes | No | No |  |  |  |  | 4681.429 | 32895.6 | 32895.6 | 32895.6 | 37577.029 | -32895.6 |  | 328956 | No | 1
2022/23 | 320 | Street Construction | Street Improvements | 320-8122-439 | Cyride Route Pavement Improvements | Lincoln Way (Beedle/Hickory Dr to Franklin Ave) | Complete | 1686000 | 62918 | WHKS | 0 | 0 | 2023/24 | 2023/24 | 2024-03-01 | 2025-01-15 | 2024/25 | 2025-01-31 | Jesus | Dean | Con-Struct | Yes | No | 1930068.29 | 1686000 |  |  | 1686000 |  |  | 1930068.29 | 1686000 | -244068.29 | No | 0 | No | 0
2022/23 | 383 | 2022/23 GO Bonds | Street Improvements | 383-8116-439 | Asphalt Street Pavement Improvements | Oakwood Rd (State Ave to University Ave) | Complete | 2000000 | 62021 | WHKS | 122800 | 122800 | 2022/23 | 2023/24 | 2024-07-06 | 2024-08-01 | 2024/25 | 2024-07-01 | Jesus | Dean | Con-Struct | No | No | 1688576.9 | 1772978.4 |  |  | 1772902.27 | 0 | 0 | 1811376.9 | 1895702.27 | 188623.1 | No | 703 | No | 0
2022/23 | 383 | 2022/23 GO Bonds | Public Safety-Fire | 383-2260-429 | Fire Station 3 PCC Replacement | 2400 S Duff Ave | Complete | 342338 | 61681 | Dean | 0 | 0 | 2022/23 | 2022/23 | 2023-04-01 | 2023-07-31 | 2023/24 | 2023-10-31 | Jared | Dean | Brothers Concrete | No | No | 264032.25 | 228269.5 |  |  | 227964.9 |  |  | 264032.25 | 227964.9 | 78305.75 | No |  | No | 1
2022/23 | 383 | 2022/23 GO Bonds | Street Improvements | 383-8101-439 | Seal Coat Street Pavement Improvements | Murray Dr (Northwestern to Grand Ave) | Complete | 750000 | 61683 | Hafiz | 0 | 0 | 2021/22 | 2022/23 | 2023-05-01 | 2024-01-10 | 2023/24 | 2024-01-31 | Jared | Hafiz | Manatt's | No | No | 609340.65 | 494593.95 |  |  | 486763.59 |  |  | 609340.65 | 486763.59 | 140659.35 | No |  | No | 0
2022/23 | 383 | 2022/23 GO Bonds | Street Improvements | 383-8116-439 | Asphalt Street Pavement Improvements | 28th St (Hoover Ave to Ferndale Ave) | Complete | 1000000 | 61495 | Dean |  |  | 2022/23 | 2022/23 | 2023-05-01 | 2023-12-31 | 2023/24 | 2023-12-31 |  | Dean | Manatt's | No | No | 840378.75 | 828193.84 |  |  | 826239.401 |  |  | 840378.75 | 826239.401 | 159621.25 | No |  | No | 0
2022/23 | 383 | 2022/23 GO Bonds | Street Improvements | 383-8154-439 | Downtown Street Improvements | North/South Alley (Adams Alley between Douglas Ave & Duff Ave) | Complete | 250000 | 61682 | Hafiz | 0 | 0 | 2022/23 | 2022/23 | 2023-04-01 | 2023-05-01 | 2022/23 | 2023-07-01 | Jared | Hafiz | Brothers Concrete | No | No | 133510 | 103062.3 |  |  | 103933.3 |  |  | 133510 | 103933.3 | 116490 | No | 0 | No | 1
2022/23 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | 28th St (Hoover Ave to Ferndale Ave) | Complete |  | 61495 | Dean | 0 | 0 | 2022/23 | 2022/23 | 2023-05-01 | 2023-12-31 | 2023/24 | 2023-12-31 |  | Dean | Manatt's | No | No | 8200 | 8613 |  |  | 8613 |  |  | 8200 | 8613 | -8200 | No |  | No | 0
2022/23 | 381 | 2020/21 GO Bonds | Street Improvements | 381-8122-489 | Cyride Route Pavement Improvements | Lincoln Way (Beedle/Hickory Dr to Franklin Ave) | Complete | 463298 | 62918 | WHKS | 0 | 0 | 2023/24 | 2023/24 | 2024-03-01 | 2025-01-15 | 2024/25 | 2025-01-31 | Jesus | Dean | Con-Struct | Yes | No | 463298 | 463298 |  |  | 463298 | 0 | 0 | 463298 | 463298 | 0 |  | 0 | No | 0
2022/23 | 520 | Sewer Utility | Sanitary Sewer System | 520-8194-439 | Sanitary Sewer system Improvements | Oakwood Rd (State Ave to University Ave) | Complete |  | 60913 |  | 0 | 0 | 2022/23 | 2023/24 | 2024-07-06 | 2024-08-01 | 2024/25 | 2024-07-01 | Jake | Dean | Country Landscapes | No | No |  |  |  |  | 32845.7 |  |  | 0 | 32845.7 | 0 |  |  | No | 1
2022/23 | 30 | Local Option Sales Tax | Street Improvements | 030-8122-489 | Shared Use Path Maintenance | Lincoln Way (Beedle/Hickory Dr to Franklin Ave) | Complete | 172500 | 62918 | WHKS | 0 | 0 | 2023/24 | 2023/24 | 2024-03-01 | 2025-01-15 | 2024/25 | 2025-01-31 | Jesus | Dean | Con-Struct | Yes | No | 47635 | 100861 |  |  | 99537.56 |  |  | 47635 | 99537.56 | 124865 | No | 71639 | No | 0
2022/23 | 530 | Electric Services | Electric Services | 530-4823-489 | Street Light and Line Relocation | Lincoln Way (Beedle/Hickory Dr to Franklin Ave) | Complete | 47635 | 62918 | Electric | 0 | 0 | 2023/24 | 2023/24 | 2024-03-01 | 2025-01-15 | 2024/25 | 2025-01-31 | Jesus | Dean | Con-Struct | Yes | No | 47635 | 47635 |  |  | 47320 |  |  | 47635 | 47320 | 0 |  | 0 | No | 0
2022/23 | 383 | 2022/23 GO Bonds | Street Improvements | 383-8122-489 | Cyride Route Pavement Improvements | Lincoln Way (Beedle/Hickory Dr to Franklin Ave) | Complete | 775000 | 62918 | WHKS | 158700 | 158700 | 2023/24 | 2023/24 | 2024-03-01 | 2025-01-15 | 2024/25 | 2025-01-31 | Jesus | Dean | Con-Struct | Yes | No | 482517.07 | 686193.2 |  |  | 641030.96 | 100000 |  | 741217.07 | 899730.96 | 33782.93 | No | 84332 | No | 0
2022/23 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Clear Water Diversion | Schubert St, Taft Ave, Wheeler St, and 20th St | Complete | 100000 | 60907 | Dean | 0 | 0 | 2021/22 | 2022/23 | 2023-04-01 | 6/31/23 | 2022/23 | 6/31/23 |  |  | Ames Trenching | No | No | 134740 | 94500 |  |  | 91500 |  |  | 134740 | 91500 | -34740 | No |  | No | 1
2022/23 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | 9th St (Brookridge Ave to Northwestern Ave) Brookridge Ave (6th St to Ridgewood Ave) Alley (6th St to 9th St) Lee St (Brookridge Ave to Ridgewood Ave) Ridgewood Ave (6th St to 9th St) | Complete | 200000 | 62065 | WHKS | 0 | 0 | 2022/23 | 2022/23 | 2023-04-25 |  | 2025/26 | 2024-12-31 | Jared | Hafiz | Shekar | No | No | 289200 | 200000 |  |  | 174341.52 | 25000 |  | 314200 | 199341.52 | -114200 | No |  | No | 0
2022/23 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | 28th St (Hoover Ave to Ferndale Ave) | Complete |  | 61495 | Dean | 0 | 0 | 2022/23 | 2022/23 | 2023-05-01 | 2023-12-31 | 2023/24 | 2023-12-31 |  | Dean | Manatt's | No | No | 2000 | 6710 |  |  | 14168 |  |  | 2000 | 14168 | -2000 | No |  | No | 1
2022/23 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | Lincoln Way (Beedle/Hickory Dr to Franklin Ave) | Complete | 60000 | 62918 | WHKS | 0 | 0 | 2023/24 | 2023/24 | 2024-03-01 | 2025-01-15 | 2024/25 | 2025-01-31 | Jesus | Dean | Con-Struct | Yes | No | 60000 | 64000 |  |  | 52000 | 0 |  | 60000 | 52000 | 0 | No | 0 | No | 1
2022/23 | 520 | Sewer Utility | Sanitary Sewer System | 520-8571-489 | Ames Plan 2040 Sanitary | N Sunset Ridge Sanitary Sewer | Complete | 604725 | 60633 | Bolton & Menk |  |  | 2022/23 | 2022/23 | 2023-03-01 | 2024-12-17 | 2023/24 | 2023/24 | Jesus | Cesar | Rognes Corp | No | No | 487621.76 | 602268.48 |  |  | 878802.12 |  |  | 487621.76 | 878802.12 | 117103.24 | No | 1094 | No | 1
2022/23 | 560 | Stormwater Utility | Stormwater | 560-8638-489 | Stormwater Erosion Control Program | Clear Creek Bank Stabilization (4921 Utah Dr) | Complete | 400000 | 62979 | WHKS | 22700 | 22700 | 2023/24 | 2023/24 | 2024-02-01 | 2024-06-30 | 2023/24 | 2024-06-30 | Jake | Hafiz | Iowa Earth Works | No | No | 102966.5 | 75615.4 |  |  | 61147.72 |  |  | 125666.5 | 83847.72 | 274333.5 | No | 0 | No | 1
2022/23 | 560 | Stormwater Utility | Stormwater | 560-8638-489 | Stormwater Erosion Control Program | Clear Creek bank Stabilization (west of Brittish Columbia Ave) | Design | 249100 |  | WHKS | 63100 |  | 2022/23 | 2024/25 |  |  | 2025/26 |  |  | Hafiz |  |  | No | [7 empty] | 63100 | 63100 | 186000 |  | 192540 | No | 1
2022/23 | 520 | Sewer Utility | Sanitary Sewer System | 520-8585-489 | Clear Water Diversion | 28th St (Hoover Ave to Ferndale Ave) | Complete |  | 61495 | Dean | 0 | 0 | 2022/23 | 2022/23 | 2023-05-01 | 2023-12-31 | 2023/24 | 2023-12-31 |  | Dean | Manatt's | No | No | 6000 | 3410 |  |  | 18062 |  |  | 6000 | 18062 | -6000 | No |  | No | 0
2022/23 | 560 | Stormwater Utility | Stormwater | 560-8642-489 | Stormwater Improvement Program | Oakwood Rd (State Ave to University Ave) | Complete |  | 62021 | WHKS | 0 | 0 | 2022/23 | 2023/24 | 2024-07-06 | 2024-08-01 | 2024/25 | 2024-07-01 | Jesus | Dean | Con-Struct | No | No | 224655 | 195594 |  |  | 193977.5 |  |  | 224655 | 193977.5 | -224655 | No | 0 | No | 0
2022/23 | 522 | Sewer Improvements (SRF) | Sanitary Sewer System | 522-8551-489 | Sanitary Sewer System Improvements | Basin 11 | Design | 2100000 |  | WHKS | 52000 |  | 2022/23 | 2024/25 |  |  | 2025/26 |  | WHKS | Hafiz |  |  | No | [7 empty] | 52000 | 52000 | 2048000 | No | 560184 | No | 1
2022/23 | 560 | Stormwater Utility | Stormwater | 560-8659-489 | Low Point Drainage Improvements | 1100 Kennedy St East Lincoln Way (2000 block) 2100/2200 Jensen Ave Barr Drive Pearle Ave Alley Harrison Road (1900 block) Northridge Lane (2800 block) Garnet Dr (700 block) Idaho Ct (1200 block) | Construction | 632146 | 64556 | Liz | 0 | 0 | 2025/26 | 2024/25 | 2025-08-01 |  | 2025/26 | 2026-06-30 |  | Mindy/Noel | Iowa Water & Waste Systems | No | No | 518000 | 523245.2 | 43282.15 |  |  | 20000 |  | 586527.35 | 20000 | 45618.65 | No | 30184.75 | No | 1
2022/23 | 522 | Sewer Improvements (SRF) | Sanitary Sewer System | 522-8552-489 | Sanitary Sewer System Improvements | US Highway 69 (Basin 12) | Complete | 725918 | 62157 | WHKS | 79500 |  | 2022/23 | 2022/23 | 2023-08-15 | 2024-03-02 | 2023/24 | 2024-05-01 | WHKS | Hafiz | Jet Drain Services, LLC | No | No | 1500000 | 1353819 |  |  | 1249017.99 |  |  | 1579500 | 1328517.99 | -853582 | No | 703132 | No | 1
2022/23 | 522 | Sewer Improvements (SRF) | Sanitary Sewer System | 522-8552-489 | Sanitary Sewer System Improvements | US 69 (Basin 12) | Design | 725918 |  | WHKS | 22786 |  | 2025/26 | 2025/26 |  |  | 2025/26 |  |  | Hafiz | [10 empty] | 22786 | 22786 | 703132 |  | 703132 |  | 1
2022/23 | 522 | Sewer Improvements (SRF) | Sanitary Sewer System | 522-8553-489 | Sanitary Sewer System Improvements | Downtown (Basin 12) | Design | 2336322 |  | WHKS | 0 | 0 | 2022/23 | 2024/25 |  |  | 2025/26 |  | WHKS | Hafiz |  |  | No | [7 empty] | 0 | 0 | 2336322 | No | 2336322 | No | 1
2023/24 | 122 | American Rescue Plan | Sanitary Sewer System | 122-8573-489 | Ames Plan 2040 Sanitary | S 500th Avenue County Line Road | Close-Out | 654121 | 63957 | Hafiz | 0 | 0 | 2024/25 | 2024/25 | 2024-12-01 | 2025-11-30 | 2024/25 | 2025-12-31 | WHKS | Hafiz | Rognes Corp | No | No | 702275 | 551057.7 | -8298.5 |  | 542759.2 | 135000 |  | 837275 | 677759.2 | -183154 | No | 69604 | No | 1
2023/24 | 520 | Sewer Utility | Sanitary Sewer System | 520-8131-489 | Sanitary Sewer System Improvements | 6th St (Brookridge Ave to Northwestern Ave) | Construction | 35000 | 63041 | Hafiz | 0 | 0 | 2023/24 | 2023/24 | 2025-08-01 |  | 2025/26 | 2026-06-01 | Jared | Hafiz | Con-Struct | No | No | 35500 | 35000 | [5 empty] | 35500 | 0 | -500 | No |  |  | 0
2023/24 | 520 | Sewer Utility | Sanitary Sewer System | 520-8501-489 | Sanitary Sewer system Improvements | Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | Close-Out | 200000 | 63042 | MSA | 0 | 0 | 2023/24 | 2023/24 | 2024-06-01 |  | 2025/26 | 2025-12-31 | Jesus | Hafiz | Con-Struct | No | No | 231475 | 381800 | 18833.29 | 12000 |  | 0 |  | 231475 | 0 | -43475 | No | 10000 | No | 1
2023/24 | 380 | 2019/20 GO Bonds | Street Improvements | 380-8131-489 | Collector Street Pavement Improvements | 6th St (Brookridge Ave to Northwestern Ave) | Construction | 120000 | 63041 | Hafiz | 0 | 0 | 2023/24 | 2023/24 | 2025-08-01 |  | 2025/26 | 2026-06-01 | Jared | Hafiz | Con-Struct | No | No | 120000 | 120000 |  |  | 54020 | 0 | 0 | 120000 | 54020 | 0 | No | 65980 | No | 0
2023/24 | 510 | Water Utility | Water Distribution | 510-8131-489 | Water System Improvements | 6th St (Brookridge Ave to Northwestern Ave) | Construction | 28000 | 63041 | Hafiz | 0 | 0 | 2023/24 | 2023/24 | 2025-08-01 |  | 2025/26 | 2026-06-01 | Jared | Hafiz | Con-Struct | No | No | 39220 | 27430 | [5 empty] | 39220 | 0 | -11220 | No | 0 | No | 0
2023/24 | 384 | 2023/24 GO Bonds | Street Improvements | 384-8131-439 | Collector Street Pavement Improvements | 6th St (Brookridge Ave to Northwestern Ave) | Construction | 1170300 | 63041 | Hafiz | 0 | 0 | 2023/24 | 2023/24 | 2025-08-01 |  | 2025/26 | 2026-06-01 | Jared | Hafiz | Con-Struct | No | No | 1141766.18 | 1003926 |  |  |  | 200000 |  | 1341766.18 | 200000 | -171466.18 | No | 358394 | No | 1
2023/24 | 60 | Road Use Tax | Street Improvements | 060-8131-489 | Collector Street Pavement Improvements | 6th St (Brookridge Ave to Northwestern Ave) | Construction | 75000 | 63041 | Hafiz | 0 | 0 | 2023/24 | 2023/24 | 2025-08-01 |  | 2025/26 | 2026-06-01 | Jared | Hafiz | Con-Struct | No | No | 75000 | 75000 |  |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | No | 0 | No | 0
2023/24 | 384 | 2023/24 GO Bonds | Street Improvements | 384-8117-439 | Asphalt Street Pavement Improvements | E 7th St. (Crawford to End) North Riverside Dr (Lincoln Way to N 3rd) | Complete | 900000 | 62905 | Dean | 0 | 0 | 2023/24 | 2023/24 | 2024-10-01 | 2025-11-04 | 2025/26 | 2025-12-31 | Scott S | Dean | Con-Struct | No | No | 832278.3 | 346298.7 | 81528.41 |  | 761082.61 | 116000 |  | 948278.3 | 877082.61 | -48278.3 | No | 172551 | No | 1
2023/24 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | East 16th St (Duff Ave to Maxwell Ave) Glendale Ave (E 13th St - E 16th St) Quebec St (4101 - Arizona Ave) Quebec Circle | Complete | 373315 | 62893 | Dean | 0 | 0 | 2023/24 | 2023/24 | 2024-05-01 | 2025-05-31 | 2025/26 | 2025-12-31 | Jared | Dean | Manatt's | No | No | 445850 | 360255.5 |  |  | 373315 | 0 |  | 445850 | 373315 | -72535 | No |  | No | 1
2023/24 | 60 | Road Use Tax | Street Improvements | 060-7770-439 | Neighborhood Curb Replacement Program | East 16th St (Duff Ave to Maxwell Ave) Glendale Ave (E 13th St - E 16th St) Quebec St (4101 - Arizona Ave) Quebec Circle | Complete | 300000 | 62893 | Dean | 0 | 0 | 2023/24 | 2023/24 | 2024-05-01 | 2025-05-31 | 2025/26 | 2025-12-31 | Jared | Dean | Manatt's | No | No | 268905 | 307042 |  |  | 124474.8 | 0 | 75500 | 268905 | 124474.8 | 31095 | No | 331421 | No | 0
2023/24 | 384 | 2023/24 GO Bonds | Street Improvements | 384-8101-439 | Seal Coat Street Pavement Improvements | East 16th St (Duff Ave to Maxwell Ave) Glendale Ave (E 13th St - E 16th St) Quebec St (4101 - Arizona Ave) Quebec Circle | Complete | 1750000 | 62893 | Dean | 0 | 0 | 2023/24 | 2023/24 | 2024-05-01 | 2025-05-31 | 2025/26 | 2025-12-31 | Jared | Dean | Manatt's | No | No | 1342729.5 | 989241.26 |  |  | 974576.39 | 130000 |  | 1472729.5 | 1104576.39 | 277270.5 | No | 610937 | No | 0
2023/24 | 384 | 2023/24 GO Bonds | Street Improvements | 384-8143-439 | Arterial Street Pavement Improvements | Airport Rd (from University Blvd to S. Riverside Dr.) | Complete | 1319224 | 63108 | Hafiz | 0 | 0 | 2023/24 | 2023/24 | 2024-05-15 | 2024-11-30 | 2024/25 | 2025-08-01 | Scott S | Hafiz | All Star Concrete | No | No | 1182320.4 | 1187598.89 |  |  | 1235121.13 | 140000 |  | 1322320.4 | 1375121.13 | -3096.4 | No | 0 | No | 0
2023/24 | 530 | Electric Services | Streetlight and Line Relocation | 530-4823-489 | Arterial Street Pavement Improvements | Airport Rd (from University Blvd to S. Riverside Dr.) | Complete | 9405 | 63108 | Hafiz | 0 | 0 | 2023/24 | 2023/24 | 2024-05-15 | 2024-11-30 | 2024/25 | 2025-08-01 | Scott S | Hafiz | All Star Concrete | No | No | 0 | 0 |  |  | 9405 |  |  | 0 | 9405 | 9405 | No | 0 | No | 0
2023/24 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | Curtiss Ave (13th St to 16th St) Marston Ave (13th St to 16th St) Phoenix Circle Roosevelt Ave (13th St to 16th St) | Complete |  | 62892 | Dean | 0 | 0 | 2023/24 | 2023/24 | 2024-05-01 | 2025-03-31 | 2024/25 | 2025-12-31 | Scott M | Dean | Manatt's | No | No | 195687.5 | 143101.05 |  |  | 167300 |  |  | 195687.5 | 167300 | -195687.5 | No |  | No | 0
2023/24 | 384 | 2023/24 GO Bonds | Street Improvements | 384-8117-439 | Asphalt Street Pavement Improvements | Curtiss Ave (13th St to 16th St) Marston Ave (13th St to 16th St) Phoenix Circle Roosevelt Ave (13th St to 16th St) | Complete |  | 62892 | Dean | 0 | 0 | 2023/24 | 2023/24 | 2024-05-01 | 2025-03-31 | 2024/25 | 2025-12-31 | Scott M | Dean | Manatt's | No | No | 1740770.5 | 1276560.52 |  |  | 1494587.37 |  |  | 1740770.5 | 1494587.37 | -1740770.5 | No | 0 | No | 0
2023/24 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | Kellogg Ave (7th St. to 13th St) 11th St (Burnett Ave to Kellogg Ave) | Close-Out | 808389.46 | 63386 | Hafiz | 0 | 0 | 2023/24 | 2023/24 | 2025-03-10 | 2025-11-25 | 2025/26 | 2025-12-31 | Scott M | Hafiz | Jet Drain Services, LLC | No | No | 910652.5 | 808389.46 | 82512.47 |  | 890901.93 | 122000 | 122000 | 1032652.5 | 1012901.93 | -224263.04 | No |  | No | 1
2023/24 | 87 | CDBG | Water Distribution | 510-8461-489 | Water System Improvements | N. Russell (N 2nd St to N 4th St) | Complete | 560000 | 64492 | Hafiz | 0 | 0 | 2024/25 | 2024/25 | 2025-05-15 | 2025-10-31 | 2025/26 | 2025-12-31 | Jesus | Hafiz | Iowa Water & Waste Systems | Yes | No | 403563 | 346858.5 | 30831.65 |  | 377690.15 | 60000 |  | 463563 | 437690.15 | 96437 | No |  | No | 1
2023/24 | 384 | 2023/24 GO Bonds | Street Improvements | 384-8117-439 | Asphalt Street Pavement Improvements | Prairie View West: Prairie View East | Complete | 545412 | 63110 | Dean | 0 | 0 | 2023/24 | 2023/24 | 2025-05-01 | 2025-10-31 | 2025/26 | 2025-12-31 | Scott S | Dean | Con-Struct | No | No | 303596.5 | 252647.9 | -26991.68 |  | 273693.5 | 70000 |  | 373596.5 | 343693.5 | 171815.5 | No | 0 | No | 0
2023/24 | 384 | 2023/24 GO Bonds | Street Improvements | 384-8169-439 | Concrete Pavement Improvements | Prairie View West: Prairie View East | Complete | 900000 | 63110 | Dean | 0 | 0 | 2023/24 | 2023/24 | 2025-05-01 | 2025-10-31 | 2025/26 | 2025-12-31 | Scott S | Dean | Con-Struct | No | No | 807706.8 | 705695.1 | 203488.8 |  | 871146.62 | 100000 |  | 907706.8 | 971146.62 | -7706.8 | No | 102396 | No | 0
2023/24 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | E 7th St. (Crawford to End) North Riverside Dr (Lincoln Way to N 3rd) | Complete | 27000 | 62905 | Dean | 0 | 0 | 2023/24 | 2023/24 | 2024-10-01 | 2025-11-04 | 2025/26 | 2025-12-31 | Scott S | Dean | Con-Struct | No | No | 19500 | 18000 | 9000 |  | 27000 |  |  | 19500 | 27000 | 7500 | No | 0 | No | 0
2023/24 | 510 | Water Utility | Water Distribution | 510-8401-489 | Water System Improvements | Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | Construction | 399800 | 63042 | MSA | 0 | 0 | 2023/24 | 2023/24 | 2024-06-01 |  | 2025/26 | 2025-12-31 | Jesus | Hafiz | Con-Struct | No | No | 251815 | 340045 | 1911.17 |  |  |  |  | 251815 | 0 | 147985 | No | 15889 | No | 0
2023/24 | 384 | 2023/24 GO Bonds | Street Improvements | 384-8191-439 | Campustown Public Improvements | Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | Construction | 982837 | 63042 | MSA | 101225 |  | 2023/24 | 2023/24 | 2024-06-01 |  | 2025/26 | 2025-12-31 | Jesus | Hafiz | Con-Struct | No | No | 847792.4 | 789902 | -181860.26 |  |  | 100000 |  | 1049017.4 | 201225 | -66180.4 | No | 117627 | No | 0
2023/24 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | East 16th St (Duff Ave to Maxwell Ave) Glendale Ave (E 13th St - E 16th St) Quebec St (4101 - Arizona Ave) Quebec Circle | Complete | 184224 | 62893 | Dean | 0 | 0 | 2023/24 | 2023/24 | 2024-05-01 | 2025-05-31 | 2025/26 | 2025-12-31 | Jared | Dean | Manatt's | No | No | 202700 | 171462.6 |  |  | 184223.1 | 25000 |  | 227700 | 209223.1 | -43476 | No |  | No | 0
2023/24 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | Curtiss Ave (13th St to 16th St) Marston Ave (13th St to 16th St) Phoenix Circle Roosevelt Ave (13th St to 16th St) | Complete |  | 62892 | Dean | 0 | 0 | 2023/24 | 2023/24 | 2024-05-01 | 2025-03-31 | 2024/25 | 2025-12-31 | Scott M | Dean | Manatt's | No | No | 91000 | 147266 |  |  | 147266 |  |  | 91000 | 147266 | -91000 | No |  | No | 1
2023/24 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | East Lincoln Way & Nikkol Trunk Line | Design |  |  | WHKS | 4500 | 4500 | 2024/25 | 2024/25 |  |  | 2025/26 |  | WHKS | Hafiz |  |  | No | [7 empty] | 4500 | 4500 | -4500 |  |  | No | 1
2023/24 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | East Lincoln Way & Nikkol Trunk Line | Design |  |  | WHKS | 20179.45 | 20179.45 | 2024/25 | 2024/25 |  |  | 2025/26 |  | WHKS | Hafiz |  |  | No | [7 empty] | 20179.45 | 20179.45 | -20179.45 |  |  | No | 0
2023/24 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | Prairie View West: Prairie View East | Complete | 58000 | 63110 | Dean | 0 | 0 | 2023/24 | 2023/24 | 2025-05-01 | 2025-10-31 | 2025/26 | 2025-12-31 | Scott S | Dean | Con-Struct | No | No | 54000 | 57100 |  |  | 47100 |  |  | 54000 | 47100 | 4000 | No | 261006 | No | 1
2023/24 | 560 | Stormwater Utility | Stormwater | 560-8639-489 | Stormwater Erosion Control Program | College Creek Bank Stabilization (Hemingway Drive) | Complete | 250000 | 64372 | WHKS | 32800 | 32800 | 2024/25 | 2024/25 | 2025-03-15 | 2025-10-31 | 2025/26 | 2025-12-31 | Jake | Hafiz | Jackson Construction, LLC | No | No | 179780 | 95143.17 | 19013.46 |  | 114156.63 | 20000 |  | 232580 | 166956.63 | 17420 |  | 0 | No | 1
2023/24 | 560 | Stormwater Utility | Stormwater | 560-8639-489 | Stormwater Erosion Control Program | Inis Grove (near restroom) | Design | 600000 |  | WHKS | 29400 |  | 2025/26 | 2025/26 |  |  | 2025/26 | [5 empty] | No | [7 empty] | 29400 | 29400 | 570600 |  | 680350 | No | 1
2023/24 | 522 | Sewer Improvements (SRF) | Sanitary Sewer System | 522-8554-489 | Sanitary Sewer System Improvements | East Lincoln Way & Nikkol Trunk Line | Design | 7500000 |  | WHKS | 272000 | 307563.19 | 2024/25 | 2024/25 |  |  | 2025/26 |  | WHKS | Hafiz |  |  | No | [7 empty] | 272000 | 272000 | 7228000 | No | 5553127 | No | 0
2024/25 | 122 | American Rescue Plan | Sanitary Sewer System | 122-8572-489 | Ames Plan 2040 Sanitary | 550th (Ken Maril Rd to 265th St) | Complete | 2336904 | 64118 | WHKS | 273000 |  | 2024/25 | 2024/25 | 2025-01-20 | 2025-10-31 | 2024/25 | 2025-12-31 | WHKS | Hafiz | S.M. Hentges & Sons, Inc | No | No | 3098434 | 2036000 |  |  |  | 305000 |  | 3676434 | 578000 | -1339530 | No | 26174 | No | 1
2024/25 | 560 | Stormwater Utility | Stormwater | 560-8183-489 | S 16th St Roadway Widening | S. 16th (University Boulevard to Apple Place) | Construction | 250000 |  | Shive Hattery | 0 | 0 | 2024/25 | 2024/25 | 2025-06-17 |  | 2026/27 | 12/31/20266 |  | Hafiz | Con-Struct | Yes | Yes | 210731.5 | 196124 | [5 empty] | 210731.5 | 0 | 39268.5 |  |  | Yes | 0
2024/25 | 560 | Stormwater Utility | Stormwater | 560-8194-439 | ROW Restoration | ROW Restoration | Close-Out |  |  | Dean | 0 | 0 | 2024/25 | 2024/25 | 2024-07-01 | [13 empty] | 22857 |  | 22857 | 22857 | -22857 |  | 278872 |  | 1
2024/25 | 560 | Stormwater Utility | Stormwater | 560-8601-489 | Stormwater Quality Improvements | Ada Hayden Sturges Tributary | Planning | 190961 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 | [5 empty] | No | [7 empty] | 0 | 0 | 190961 |  | 173477 | No | 1
2024/25 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | East Lincoln Way (Teller Ave to Potter Ave) | Complete |  | 59817 | Stanley Consultants | 0 | 0 | 2020/21 | 2020/21 | 2021-11-01 | 2023-06-01 | 2024/25 | 2023-06-01 | Jesus | Dean | Keller | EDA | No | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | Yes | 0 | Yes | 0
2024/25 | 510 | Water Utility | Water Distribution | 510-8465-489 | Water System Improvements | E. 14th St. (Glendale to Meadowlane) Meadowlane (E. 13th St. to E. 14th St.) | Construction | 380000 | 64734 | Hafiz | 0 | 0 | 2025/26 | 2025/26 | 2025-10-01 |  | 2025/26 | 2025-12-31 | Jesus | Hafiz | Jet Drain Services, LLC | No | No | 330216 | 314426 |  |  |  | 45000 |  | 375216 | 45000 | 4784 | No |  |  | 1
2024/25 | 380 | 2019/20 GO Bonds | Street Improvements | 380-8184-439 | Arterial Street Pavement Improvements | Hyland Ave (Lincoln Way to Ontario St) | Construction | 220890 | 64389 | WHKS | 0 | 0 | 2024/25 | 2024/25 | 2025-05-31 |  | 2025/26 | 2027-12-31 | Jesus | Dean | All Star Concrete | Yes | No | 220890 | 220890 | [5 empty] | 220890 | 0 | 0 | No | 65198 |  | 0
2024/25 | 381 | 2020/21 GO Bonds | Street Improvements | 381-8184-439 | Arterial Street Pavement Improvements | Hyland Ave (Lincoln Way to Ontario St) | Construction | 510000 | 64389 | WHKS | 0 | 0 | 2024/25 | 2024/25 | 2025-05-31 |  | 2025/26 | 2027-12-31 | Jesus | Dean | All Star Concrete | Yes | No | 510000 | 510000 |  |  |  | 200000 |  | 710000 | 200000 | -200000 | No | 163313 | Yes | 0
2024/25 | 320 | Street Construction | Street Improvements | 320-8184-439 | Arterial Street Pavement Improvements | Hyland Ave (Lincoln Way to Ontario St) | Construction | 1890000 | 64389 | WHKS | 142200 | 122018 | 2024/25 | 2024/25 | 2025-05-31 |  | 2025/26 | 2027-12-31 | Jesus | Dean | All Star Concrete | Yes | No | 1747800 | 1260304.05 |  |  |  | 263700 |  | 2153700 | 405900 | -263700 | No | 1890000 | No | 1
2024/25 | 87 | CDBG | Water Distribution | -87 | Water System Improvements | S. Russell (S 4th to Lincoln Way) | Construction | 680000 |  | Hafiz | 0 | 0 | 2025/26 | 2025/26 | 2025-10-27 |  | 2025/26 | 2026-12-31 | Jesus | Hafiz | Iowa Water & Waste Systems | Yes | No | 575908 | 484024.4 |  |  |  | 80000 |  | 655908 | 80000 | 24092 | No |  | No | 1
2024/25 | 560 | Stormwater Utility | Stormwater | 560-8605-489 | Stormwater System Analysis | Stormwater System Analysis | Design | 642257 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2026/27 | [5 empty] | No | [7 empty] | 0 | 0 | 642257 |  | 637905 | No | 1
2024/25 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | US Highway 69 (Ken Maril Rd to South Past Waterway) | Complete | [5 empty] | 2023/24 | 2023/24 | 2023-05-01 | 2023-11-16 | 2023/24 | 2024-12-01 | Jesus | Hafiz |  | ARPA | No | [7 empty] | 0 | 0 | 0 |  |  | No | 1
2024/25 | 381 | 2020/21 GO Bonds | Street Improvements | 381-8132-439 | Collector Street Pavement Improvements | Oakland St. (Oliver Ave to Hawthorne Ave) | Construction | 193790 | 64739 | Hafiz | 0 | 0 | 2024/25 | 2024/25 | 2025-07-21 |  | 2025/26 | 2027-05-31 | Scott Shepard | Hafiz | Manatt's | NO | No | 193790 | 193790 |  |  |  | 100000 |  | 293790 | 100000 | -100000 |  | 193790 | No | 1
2024/25 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | N. Russell (Lincoln Way to N 2nd St) | Complete | 200000 | 63866 | Hafiz | 0 | 0 | 2024/25 | 2024/25 | 2024-11-01 | 2025-07-15 | 2024/25 | 2025-05-01 | Scott M | Hafiz | Iowa Water & Waste Systems | No | No | 171856.5 | 104910.5 | -202 | 20000 | 104708.5 | 20000 |  | 191856.5 | 124708.5 | -11856.5 | No |  | No | 1
2024/25 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | Lincoln Way (Wilder Ave to County Line) | Complete | [5 empty] | 2023/24 | 2023/24 | 2023-05-01 | 2023-11-06 | 2023/24 | 2024-12-01 | Jesus | Hafiz |  | ARPA | No | [7 empty] | 0 | 0 | 0 |  |  | No | 1
2024/25 | 382 | 2021/22 GO Bonds | Street Improvements | 382-8132-439 | Collector Street Pavement Improvements | Oakland St. (Oliver Ave to Hawthorne Ave) | Construction | 419675 | 64739 | Hafiz | 0 | 0 | 2024/25 | 2024/25 | 2025-07-21 |  | 2025/26 | 2027-05-31 | Scott Shepard | Hafiz | Manatt's | No | No | 261297.95 | 227054.95 | [5 empty] | 261297.95 | 0 | 158377.05 |  | 119328 | No | 0
2024/25 | 383 | 2022/23 GO Bonds | Street Improvements | 383-8132-439 | Collector Street Pavement Improvements | Oakland St. (Oliver Ave to Hawthorne Ave) | Construction | 124529 | 64739 | Hafiz | 0 | 0 | 2024/25 | 2024/25 | 2025-07-21 |  | 2025/26 | 2027-05-31 | Scott Shepard | Hafiz | Manatt's | No | No | 136535 | 136535 | 9625 |  |  |  |  | 136535 | 0 | -12006 |  | 124529 | No | 0
2024/25 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | Douglas Ave (16th St to 17th St) Barr Drive 17th St (Douglas Ave to West St) | Design | 1200000 |  | Hafiz | 0 | 0 | 2024/25 | 2024/25 |  |  | 2025/26 |  | Jesus | Hafiz |  |  | No | [7 empty] | 0 | 0 | 1200000 |  |  | No | 1
2024/25 | 60 | Road Use Tax | Street Improvements | 060- | Arterial Street Pavement Improvements | 24th St (Grand Ave east and west - 300' each) | Planning | [5 empty] | 2027/28 | 2027/28 |  |  | 2028/29 | [5 empty] | No | [7 empty] | 0 | 0 | 0 |  |  | No | 1
2024/25 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | Oakland St. (Oliver Ave to Hawthorne Ave) | Construction | 350000 | 64739 | Hafiz | 0 | 0 | 2024/25 | 2024/25 | 2025-07-21 |  | 2025/26 | 2027-05-31 | Scott Shepard | Hafiz | Manatt's | No | No | 242775 | 242775 | 6050 |  |  |  |  | 242775 | 0 | 107225 |  | 0 | No | 0
2024/25 | 320 | Street Construction | Street Improvements | 320-8183-439 | S 16th St Roadway Widening | S. 16th (University Boulevard to Apple Place) | Construction | 2814000 |  | Shive Hattery | 0 | 0 | 2024/25 | 2024/25 | 2025-06-17 |  | 2026/27 | 2026-12-31 |  | Hafiz | Con-Struct | Yes | Yes | 3366596.4 | 2867876 |  |  |  | 147750 |  | 3514346.4 | 147750 | -700346.4 |  | 2814000 | Yes | 0
2024/25 | 383 | 2022/23 GO Bonds | Street Improvements | 383-8183-439 | S 16th St Roadway Widening | S. 16th (University Boulevard to Apple Place) | Construction | 463298 |  | Shive Hattery | 0 | 0 | 2024/25 | 2024/25 | 2025-06-17 |  | 2026/27 | 2026-12-31 |  | Hafiz | Con-Struct | Yes | Yes | 463298 | 463298 | [5 empty] | 463298 | 0 | 0 |  | 0 | Yes | 0
2024/25 | 384 | 2023/24 GO Bonds | Street Improvements | 384-8183-439 | S 16th St Roadway Widening | S. 16th (University Boulevard to Apple Place) | Construction | 210669 |  | Shive Hattery | 302250 |  | 2024/25 | 2024/25 | 2025-06-17 |  | 2026/27 | 2026-12-31 |  | Hafiz | Con-Struct | Yes | Yes | 98534.1 | 98534.1 | [5 empty] | 400784.1 | 302250 | -190115.1 |  | 87158 | Yes | 1
2024/25 | 384 | 2023/24 GO Bonds | Street Improvements | 384-8183-439 | S 16th St Roadway Widening | S. 16th (University Boulevard to Apple Place) | Construction | 9970 |  | Shive Hattery | 0 | 0 | 2024/25 | 2024/25 | 2025-06-17 |  | 2026/27 | 2026-12-31 |  | Hafiz | CMT |  |  | 9970 | 9970 | [5 empty] | 9970 | 0 | 0 |  | 0 | Yes | 0
2024/25 | 87 | CDBG | Water Distribution | 087- | Water System Improvements | S. Riverside (S. 4th St to Lincoln Way) | Construction | 700000 |  | Hafiz | 0 | 0 | 2025/26 | 2025/26 | 2025-10-27 |  | 2025/26 | 2026-12-31 | Jesus | Hafiz | Iowa Water & Waste Systems | Yes | No | 600702 | 559321.3 |  |  |  | 90000 |  | 690702 | 90000 | 9298 | No |  | No | 1
2022/23 | 122 | American Rescue Plan | Sanitary Sewer System | 122-8520-489 | Ames Plan 2040 Sanitary | E 13th St (S. Dayton Ave to East of I-35) | Close-Out | 2300000 | 62500 | WHKS | 98700 | 98700 | 2024/25 | 2024/25 | 2023-10-23 | 2024-09-01 | 2024/25 | 2024-12-31 | WHKS | Hafiz | On-Track | No | No | 2833264.5 | 2125500 | 209782.96 |  | 2282092.96 | 0 | 0 | 2931964.5 | 2380792.96 | -631964.5 | No | 60000 | No | 1
2024/25 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | Hyland Ave (Lincoln Way to Ontario St) | Construction | 20500 | 64389 | WHKS | 0 | 0 | 2024/25 | 2024/25 | 2025-05-31 |  | 2025/26 | 2027-12-31 | Jesus | Dean | All Star Concrete | Yes | No | 20500 | 20500 | [5 empty] | 20500 | 0 | 0 | No |  | No | 0
2024/25 | 520 | Sewer Utility | Sanitary Sewer System | 520-8572-489 | Ames Plan 2040 Sanitary | 550th (Ken Maril Rd to 265th St) | Complete | 200000 | 64118 | WHKS | 0 | 0 | 2024/25 | 2024/25 | 2025-01-20 | 2025-10-31 | 2024/25 | 2025-12-31 | WHKS | Hafiz | S.M. Hentges & Sons, Inc | No | No | 0 | 0 |  |  | 167994 |  |  | 0 | 167994 | 200000 | No | 32006 | No | 0
2024/25 | 520 | Sewer Utility | Sanitary Sewer System | 520-8585-489 | Clear Water Diversion | Douglas Ave (14th to 16th) | Complete | 125835 | 63650 | Dean | 0 | 0 | 2023/24 | 2024/25 | 2024-07-01 | 2025-05-01 | 2024/25 | 2025-05-01 |  | Dean | Iowa Water & Waste Systems | No | No | 108000 | 90681 |  |  | 72848 | 12000 |  | 120000 | 84848 | 5835 | No |  | No | 1
2024/25 | 560 | Stormwater Utility | Stormwater | 560-8640-489 | Stormwater Erosion Control Program | Clear Creek Bank Stablization (west of North Dakota Ave) | Design | 350000 |  | Hafiz |  |  | 2026/27 | 2026/27 |  |  | 2027/28 |  |  | Hafiz |  | No | No | [7 empty] | 0 | 0 | 350000 |  | 350000 | No | 1
2024/25 | 560 | Stormwater Utility | Stormwater | 560-8653-489 | Low Point Drainage Improvements | South of Ken Maril Road (extend earthen berm behind 300/400 blocks) and Crystal drainage ditch(east of Crystal Street cul-de-sac) | Planning | 350000 |  |  |  |  | 2025/26 | 2026/27 |  |  | 2026/27 | [5 empty] | No | [7 empty] | 0 | 0 | 350000 |  | 35000 | No | 1
2025/26 | 560 | Stormwater Utility | Stormwater | 560-8642-489 | Stormwater Improvement Program | 25/26 Sanitary and Storm Televising | Complete | 50000 |  | Hafiz | 0 | 0 | 2025/26 | 2025/26 | 2025-08-01 | 2025-09-15 | 2025/26 | [5 empty] | No | 49942.46 | 49942.46 | 0 |  | 49942.46 | 0 | 0 | 49942.46 | 49942.46 | 57.54 |  | 0 |  | 1
2025/26 | 560 | Stormwater Utility | Stormwater | 560-8659-489 | Low Point Drainage Improvements | 6th St / Duff Ave 20th St / Northwestern Ave S Bell Ave / SE 16th St Grove Ave / River Oak Dr | Design | 500000 |  | Noel | 0 | 0 | 2025/26 | 2026/27 |  |  | 2026/27 |  |  | Mindy/Noel |  | No | No | [7 empty] | 0 | 0 | 500000 |  | 496409 | No | 1
2025/26 | 386 | 2025/26 GO Bonds | Street Improvements | 386-8172-439 | Alley Pavement Improvement Program | Alley south of Lincoln Way (S. Kellogg Ave to Sherman Ave) | Design | 400000 |  | Hafiz | 0 | 0 | 2025/26 | 2025/26 |  |  | 2026/27 |  |  | Hafiz |  | No | No | 160000 |  |  |  |  | 21400 |  | 181400 | 21400 | 218600 |  | 399271 | No | 1
2025/26 | 386 | 2025/26 GO Bonds | Street Improvements | 386-8133-439 | Collector Street Pavement Improvements | Bloomington Road (GW Carver to Eisenhower Ave) | Design | 500000 |  | Stanley Consultants | 72000 |  | 2025/26 | 2025/26 |  |  | 2026/27 | 2026-12-31 |  | Dean |  | No | Yes | 254015.5 |  |  |  |  | 123000 |  | 449015.5 | 195000 | 50984.5 |  | 427330 | Yes | 1
2025/26 | 30 | Local Option Sales Tax | Shared Use Paths | 030-881-439 | Shared Use Path Maintenance | Bloomington Road (GW Carver to Eisenhower Ave) | Design | 100000 |  | Stanley Consultants | 0 |  | 2025/26 | 2025/26 |  |  | 2026/27 | 2026-12-31 |  | Dean |  | No | Yes | 103371 |  |  |  |  | 0 | 0 | 103371 | 0 | -3371 |  | 100000 | Yes | 0
2025/26 | 320 | Street Construction | Street Improvements | 320-8133-439 | Collector Street Pavement Improvements | Bloomington Road (GW Carver to Eisenhower Ave) | Design | 700000 |  | Stanley Consultants | 0 |  | 2025/26 | 2025/26 |  |  | 2026/27 | 2026-12-31 |  | Dean |  | No | Yes | 700000 |  |  |  |  | 0 | 0 | 700000 | 0 | 0 |  | 700000 | Yes | 0
2025/26 | 520 | Sewer Utility | Sanitary Sewer System | 520-8160-489 | Sanitary Sewer System Improvements | Campus Ave (Lincoln Way to Oakland St) | Design | 80000 |  | WHKS | 0 |  | 2025/26 | 2025/26 |  |  | 2026/27 | 2027-06-30 |  | Dean |  |  | No | 69900 |  |  |  |  | 0 | 0 | 69900 | 0 | 10100 |  |  | Yes | 0
2025/26 | 386 | 2025/26 GO Bonds | Street Improvements | 386-8160-439 | Concrete Pavement Improvements | Campus Ave (Lincoln Way to Oakland St) | Design | 1450000 |  | WHKS | 321000 |  | 2025/26 | 2025/26 |  |  | 2026/27 | 2027-06-30 |  | Dean |  | No | No | 963667.75 |  |  |  |  | 129000 |  | 1413667.75 | 450000 | 36332.25 |  | 1899250.5 | Yes | 1
2025/26 | 510 | Water Utility | Water Distribution | 510-8159-489 | Water System Improvements | Clark Ave (9th St to 13th St) | Design | 512000 |  | WHKS | 0 | 0 | 2025/26 | 2025/26 |  |  | 2026/27 | 2027-06-30 |  | Dean |  | No | No | 511375 |  |  |  |  | 0 | 0 | 511375 | 0 | 625 |  |  | Yes | 0
2025/26 | 520 | Sewer Utility | Sanitary Sewer System | 520-8159-489 | Clear Water Diversion | Clark Ave (9th St to 13th St) | Design | 53000 |  | WHKS | 0 | 0 | 2025/26 | 2025/26 |  |  | 2026/27 | 2027-06-30 |  | Dean |  | No | No | 52500 |  |  |  |  | 0 | 0 | 52500 | 0 | 500 |  |  | Yes | 0
2025/26 | 560 | Stormwater Utility | Stormwater | 560- | Right-of-Way Restoration | City-Wide | Planning | 50000 |  | Dean | 0 |  | 2025/26 | 2025/26 |  |  | 2025/26 | [6 empty] | 10000 |  |  |  |  | 40000 |  | 50000 | 40000 | 0 |  |  |  | 0
2025/26 | 520 | Sewer Utility | Sanitary Sewer System | 520- | Right-of-Way Restoration | City-Wide | Planning | 75000 |  | Dean | 0 |  | 2025/26 | 2025/26 |  |  | 2025/26 | [6 empty] | 35000 |  |  |  |  | 40000 |  | 75000 | 40000 | 0 |  |  |  | 0
2025/26 | 60 | Road Use Tax | Street Improvements | 060-8194-439 | Right-of-Way Restoration | City-Wide | Planning | 125000 |  | Dean | 0 |  | 2025/26 | 2025/26 |  |  | 2025/26 | [6 empty] | 85000 |  |  |  |  | 40000 |  | 125000 | 40000 | 0 |  |  |  | 0
2025/26 | 510 | Water Utility | Water Distribution | 510- | Right-of-Way Restoration | City-Wide | Planning | 75000 |  | Dean | 0 |  | 2025/26 | 2025/26 |  |  | 2025/26 | [6 empty] | 35000 |  |  |  |  | 40000 |  | 75000 | 40000 | 0 |  |  |  | 0
2025/26 | 383 | 2022/23 GO Bonds | Street Improvements | 383-8150-439 | Downtown Street Improvements | East/West alley north of Lincoln Way (Sherman Ave to Kellogg Ave) | Design | 250000 |  | Hafiz | 0 | 0 | 2025/26 | 2025/26 | [5 empty] | Hafiz |  | No | No | 180000 |  |  |  |  | 24000 |  | 204000 | 24000 | 46000 |  | 250000 |  | 1
2025/26 | 60 | Road Use Tax | Street Rehabilitation | 060-7770-439 | Neighborhood Curb Replacement Program | Ferndale Ave (20th St to 24th St) Furman Drive | Design | 150000 |  | Hafiz | 0 | 0 | 2025/26 | 2025/26 |  |  | 2026/27 |  |  | Hafiz |  | No | No | 330959 |  |  |  |  | 0 |  | 330959 | 0 | -180959 |  | 481421 | No | 1
2025/26 | 386 | 2025/26 GO Bonds | Street Improvements | 386-8101-489 | Seal Coat Street Pavement Improvements | Ferndale Ave (20th St to 24th St) Furman Drive | Design | 1000000 |  | Hafiz | 0 | 0 | 2025/26 | 2025/26 |  |  | 2026/27 |  |  | Hafiz |  | No | No | 1884000 |  |  |  |  | 200000 |  | 2084000 | 200000 | -1084000 |  | 1480000 | No | 0
2025/26 | 510 | Water Utility | Water Distribution | 510-8461-489 | Water System Improvements | Ferndale Ave (20th St to 24th St) Furman Drive | Design | 680000 |  | Hafiz | 0 | 0 | 2025/26 | 2025/26 |  |  | 2026/27 |  |  | Hafiz |  | No | No | 587875 |  |  |  |  | 0 |  | 587875 | 0 | 92125 |  | 680000 | No | 0
2025/26 | 520 | Sewer Utility | Sanitary Sewer System | 520-7525-489 | Sanitary Sewer System Improvements | Grand & 13th Intersection | Design | 68000 |  | WHKS | 0 |  | 2026/27 | 2026/27 |  |  | 2027/28 |  |  | Mark |  | No | No | 68000 |  |  |  |  | 0 |  | 68000 | 0 | 0 |  |  |  | 1
2025/26 | 510 | Water Utility | Water Distribution | 510-7525-489 | Water System Improvements | Grand & 13th Intersection | Design | 690000 |  | WHKS | 0 | 0 | 2026/27 | 2026/27 |  |  | 2027/28 |  |  | Mark |  | No | No | 690000 |  |  |  |  | 0 |  | 690000 | 0 | 0 |  |  |  | 0
2025/26 | 520 | Sewer Utility | Sanitary Sewer System | 520-8521-489 | Sanitary Sewer System Improvements | Highway 30 Sanitary Sewer Relocation | Bidding | 400000 |  | WHKS | 14000 | 7844 | 2025/26 | 2025/26 |  |  |  |  | Jared | Mindy | Peterson Contractors Inc. |  |  | 350000 | 322189.3 |  |  |  | 14000 |  | 378000 | 28000 | 22000 | No | 386000 | No | 1
2025/26 | 560 | Stormwater Utility | Stormwater | 560-8118-489 | Stormwater Improvement Program | Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | Design | 60000 |  | HR Green | 0 |  | 2025/26 | 2025/26 |  |  | 2026/27 |  |  | Hafiz |  | No | No | 57000 |  |  |  |  | 0 |  | 57000 | 0 | 3000 |  |  | Yes | 0
2025/26 | 520 | Sewer Utility | Sanitary Sewer System | 520-8118-489 | Sanitary Sewer System Improvements | Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | Design | 100000 |  | HR Green | 0 |  | 2025/26 | 2025/26 |  |  | 2026/27 |  |  | Hafiz |  | No | No | 80000 |  |  |  |  | 0 |  | 80000 | 0 | 20000 |  |  | Yes | 0
2025/26 | 386 | 2025/26 GO Bonds | Street Improvements | 386-8118-489 | Asphalt Street Pavement Improvements | Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | Design | 4000000 |  | HR Green | 302000 |  | 2025/26 | 2025/26 |  |  | 2026/27 |  |  | Hafiz |  | No | No | 3340000 |  |  |  |  | 300000 |  | 3942000 | 602000 | 58000 |  |  | Yes | 1
2025/26 | 510 | Water Utility | Water Distribution | 510-8118-489 | Water System Improvements | Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | Design | 230000 |  | HR Green | 0 | 0 | 2025/26 | 2025/26 |  |  | 2026/27 |  |  | Hafiz |  | No | No | 200000 |  |  |  |  | 0 |  | 200000 | 0 | 30000 |  |  | Yes | 0
2025/26 | 520 | Sewer Utility | Sanitary Sewer System | 520-8542-489 | Sanitary Sewer System Improvements | Moore Memorial Park Sanitary Sewer Lining | Design | 0 |  | WHKS | 13400 |  | 2025/26 | 2025/26 | [5 empty] | Mindy |  |  |  | 148640 |  |  |  |  | 15000 |  | 177040 | 28400 | -177040 |  |  |  | 1
2025/26 | 560 | Stormwater Utility | Stormwater | 560-8161-489 | Stormwater Improvement Program | Sunset Drive (Ash Ave to Beach Ave) | Design | 270000 |  | WHKS | 0 | 0 | 2025/26 | 2025/26 |  |  | 2026/27 | 2027-06-30 |  | Dean |  | No | No | 268050 |  |  |  |  | 0 |  | 268050 | 0 | 1950 |  |  |  | 0
2025/26 | 520 | Sewer Utility | Sanitary Sewer System | 520-8161-489 | Sanitary Sewer System Improvements | Sunset Drive (Ash Ave to Beach Ave) | Design | 95000 |  | WHKS | 0 | 0 | 2025/26 | 2025/26 |  |  | 2026/27 | 2027-06-30 |  | Dean |  | No | No | 93000 |  |  |  |  | 0 |  | 93000 | 0 | 2000 |  |  |  | 0
2025/26 | 386 | 2025/26 GO Bonds | Street Improvements | 386-8161-439 | Concrete Pavement Improvements | Sunset Drive (Ash Ave to Beach Ave) | Design | 1100000 |  | WHKS | 0 | 0 | 2025/26 | 2025/26 |  |  | 2026/27 | 2027-06-30 |  | Dean |  | No | No | 958272.13 |  |  |  |  | 130000 |  | 1088272.13 | 130000 | 11727.87 |  | 1899250.5 | Yes | 1
2025/26 | 510 | Water Utility | Water Distribution | 510-8161-489 | Water System Improvements | Sunset Drive (Ash Ave to Beach Ave) | Design | 340000 |  | WHKS | 0 | 0 | 2025/26 | 2025/26 |  |  | 2026/27 | 2027-06-30 |  | Dean |  | No | No | 333490 |  |  |  |  | 0 |  | 333490 | 0 | 6510 |  |  |  | 0
2025/26 | 560 | Stormwater Utility | Stormwater | 560-8601-489 | Stormwater Quality Improvements | Animal Shelter Site | Design | 100000 |  |  |  |  | 2025/26 | 2025/26 |  |  | 2026/27 | 2027-06-30 | [12 empty] | 0 | 0 | 100000 |  |  |  | 1
2025/26 | 560 | Stormwater Utility | Stormwater | 560-8634-489 | Stormwater Erosion Control Program | Worrell Creek Bank Stabilization (south of Mortensen Pkwy from Gateway Hill Park Dr to University Blvd) | Design | 850000 |  | Bolten & Menk | 90000 |  | 2025/26 | 2025/26 |  |  | 2026/27 | 2027-06-30 |  | Noel |  | No | No | 670000 |  |  |  |  | 90000 |  | 850000 | 180000 | 0 |  | 612000 | Yes | 1
2026/27 | 320 | Street Construction | Street Improvements | 320- | Arterial Street Pavement Improvements | East Lincoln Way (Duff Ave to the Skunk River) | Planning | 2880000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 |  |  | Dean |  |  | Yes | [7 empty] | 0 | 0 | 2880000 |  |  | Yes | 0
2026/27 | 387 | 2026/27 GO Bonds | Street Improvements | 387- | Arterial Street Pavement Improvements | East Lincoln Way (Duff Ave to the Skunk River) | Planning | 1260000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 |  |  | Dean |  |  | Yes | [5 empty] | 650000 |  | 650000 | 650000 | 610000 |  |  |  | 1
2026/27 | 387 | 2026/27 GO Bonds | Street Improvements | 387- | Asphalt Street Pavement Improvements | Toronto St (N Dakota Ave to Garfield Ave) Garfield Ave (north of Ontario St) Woodstock Ave Windsor Court | Planning | 2340000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 | [5 empty] | No | [7 empty] | 0 | 0 | 2340000 |  |  | No | 1
2026/27 | 520 | Sewer Utility | Sanitary Sewer System | 520- | Clear Water Diversion | Washington Ave (Lincoln Way to S 3rd St) | Planning | 150000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 | [5 empty] | No | [7 empty] | 0 | 0 | 150000 |  |  | No | 0
2026/27 | 387 | 2026/27 GO Bonds | Street Improvements | 387- | Collector Street Pavement Improvements | State Avenue | Planning | 2800000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 | [5 empty] | No | [5 empty] | 500000 |  | 500000 | 500000 | 2300000 |  |  |  | 1
2026/27 | 387 | 2026/27 GO Bonds | Street Improvements |  | Concrete Pavement Improvements | North Loop Dr 9th St (Roosevelt Ave to Grand Ave) Gaskill Dr (250' S of Friley Rd. to Country Club Blvd) Crawford Ave (end to E. 9th St) | Planning | 3350000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 | [5 empty] | No | [7 empty] | 0 | 0 | 3350000 |  |  | No | 1
2026/27 | 383 | 2022/23 GO Bonds | Street Improvements | 383-8122-439 | Cyride Route Pavement Improvements | Lincoln Way (Hayward Ave to Beach Ave) | Planning | 2000000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 | [5 empty] | No | [7 empty] | 0 | 0 | 2000000 |  |  | No | 1
2026/27 | 560 | Stormwater Utility | Stormwater | 560-8603-489 | Detention-Retention Maintenance | Ada Hayden Wetlands | Planning | 150000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 | [5 empty] | No | [7 empty] | 0 | 0 | 150000 |  |  | No | 1
2026/27 | 560 | Stormwater Utility | Stormwater | 560- | Low Point Drainage Improvements | 6th St Crystal Street (200 Block) | Planning | 250000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 | [5 empty] | No | [7 empty] | 0 | 0 | 250000 |  |  | No | 1
2026/27 | 560 | Stormwater Utility | Stormwater | 560- | Low Point Drainage Improvements | Grand Ave Underpass | Planning | [5 empty] | 2026/27 | 2026/27 |  |  | 2027/28 | [13 empty] | 0 | 0 | 0 |  |  |  | 1
2026/27 | 60 | Road Use Tax | Street Rehabilitation | 060-7770-439 | Neighborhood Curb Replacement Program | Washington Ave (Lincoln Way to S 3rd St) | Planning | 150000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 | [5 empty] | No | [7 empty] | 0 | 0 | 150000 |  |  | No | 0
2026/27 | 560 | Stormwater Utility | Stormwater | 560- | Right-of-Way Restoration | City-Wide | Planning | 50000 |  | Dean | 0 |  | 2026/27 | 2026/27 |  |  | 2027/28 | [13 empty] | 0 | 0 | 50000 |  |  |  | 0
2026/27 | 520 | Sewer Utility | Sanitary Sewer System | 520- | Right-of-Way Restoration | City-Wide | Planning | 75000 |  | Dean | 0 |  | 2026/27 | 2026/27 |  |  | 2027/28 | [13 empty] | 0 | 0 | 75000 |  |  |  | 0
2026/27 | 60 | Road Use Tax | Street Improvements | 060- | Right-of-Way Restoration | City-Wide | Planning | 125000 |  | Dean | 0 |  | 2026/27 | 2026/27 |  |  | 2027/28 | [13 empty] | 0 | 0 | 125000 |  |  |  | 0
2026/27 | 510 | Water Utility | Water Distribution | 510- | Right-of-Way Restoration | City-Wide | Planning | 75000 |  | Dean | 0 |  | 2026/27 | 2026/27 |  |  | 2027/28 | [13 empty] | 0 | 0 | 75000 |  |  |  | 0
2026/27 | 520 | Sewer Utility | Sanitary Sewer System | 520- | Sanitary Sewer System Improvements | East Lincoln Way (Duff Ave to the Skunk River) | Planning | 610000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 |  |  | Dean |  |  | Yes | [7 empty] | 0 | 0 | 610000 |  |  |  | 0
2026/27 | 520 | Sewer Utility | Sanitary Sewer System | 520- | Sanitary Sewer System Improvements | North Loop Dr 9th St (Roosevelt Ave to Grand Ave) Gaskill Dr (250' S of Friley Rd. to Country Club Blvd) Crawford Ave (end to E. 9th St) | Planning | 30000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 | [13 empty] | 0 | 0 | 30000 |  |  |  | 0
2026/27 | 520 | Sewer Utility | Sanitary Sewer System | 520- | Sanitary Sewer System Improvements | Toronto St (N Dakota Ave to Garfield Ave) Garfield Ave (north of Ontario St) Woodstock Ave Windsor Court | Planning | 70000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 | [13 empty] | 0 | 0 | 70000 |  |  |  | 0
2026/27 | 387 | 2026/27 GO Bonds | Street Improvements | 387- | Seal Coat Street Pavement Improvements | Washington Ave (Lincoln Way to S 3rd St) | Planning | 900000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 | [5 empty] | No | [7 empty] | 0 | 0 | 900000 |  |  | No | 1
2026/27 | 560 | Stormwater Utility | Stormwater | 560-8641-489 | Stormwater Erosion Control Program | Canterbury Court | Planning | 350000 |  | Noel | 0 |  | 2026/27 | 2026/27 |  |  | 2027/28 |  |  | Noel |  | No | No | 300000 |  |  |  |  | 50000 |  | 350000 | 50000 | 0 |  | -683 | No | 1
2026/27 | 560 | Stormwater Utility | Stormwater |  | Stormwater Erosion Control Program | Ioway Creek (Stange Rd at Veenker Golf Course) | Planning | 200000 |  |  |  |  | 2026/27 | 2026/27 |  |  | 2027/28 |  |  | Noel |  | No | No | [7 empty] | 0 | 0 | 200000 |  |  | No | 1
2026/27 | 510 | Water Utility | Water Distribution | 510- | Water System Improvements | East Lincoln Way (Duff Ave to the Skunk River) | Planning | 300000 |  |  |  |  | 2026/27 | 2026/27 |  | 2027/28 | 2027/28 |  |  | Dean |  |  | Yes | [7 empty] | 0 | 0 | 300000 |  |  |  | 0
2027/28 | 387 | 2026/27 GO Bonds | Street Improvements | 387-8134-439 | Collector Street Pavement Improvements | West Street (Crane Ave to Hillcrest Ave) | Planning | 1500000 |  |  |  |  | 2027/28 | 2027/28 |  |  | 2027/28 | [5 empty] | No | [7 empty] | 0 | 0 | 1500000 |  |  | No | 1
2027/28 | 560 | Stormwater Utility | Stormwater | 560- | Right-of-Way Restoration | City-Wide | Planning | 50000 |  | Dean | 0 |  | 2027/28 | 2027/28 |  |  | 2027/28 | [13 empty] | 0 | 0 | 50000 |  |  |  | 0
2027/28 | 520 | Sewer Utility | Sanitary Sewer System | 520- | Sanitary Sewer System Improvements | Duff Ave (6th St to 13th St) | Planning | 850000 |  |  |  |  | 2027/28 | 2027/28 |  |  | 2027/28 | [13 empty] | 0 | 0 | 850000 |  |  |  | 1
2027/28 | 520 | Sewer Utility | Sanitary Sewer System | 520- | Right-of-Way Restoration | City-Wide | Planning | 75000 |  | Dean | 0 |  | 2027/28 | 2027/28 |  |  | 2027/28 | [13 empty] | 0 | 0 | 75000 |  |  |  | 0
2027/28 | 388 | 2027/28 GO Bonds | Street Improvements | 388-8135-439 | Collector Street Pavement Improvements | Wheeler Street (Hoover Ave to Roy Key Ave) | Planning | 1500000 |  |  |  |  | 2027/28 | 2027/28 |  |  | 2028/29 | [5 empty] | No | [7 empty] | 0 | 0 | 1500000 |  |  | No | 1
2027/28 |  | #N/A |  |  | South Skunk River Improvements | SE 16th St Ped Bridge | Planning | [5 empty] | 2027/28 | 2027/28 |  |  | 2028/29 | [5 empty] | No | [7 empty] | 0 | 0 | 0 |  |  | No | 1
2027/28 | 60 | Road Use Tax | Street Rehabilitation | 060-7770-439 | Neighborhood Curb Replacement Program | Washington Ave (S 3rd St to S 4th St) S 4th St (Walnut to East End) | Planning | 150000 |  |  |  |  | 2027/28 | 2027/28 |  |  | 2028/29 | [5 empty] | No | [7 empty] | 0 | 0 | 150000 |  |  | No | 0
2027/28 | 388 | 2027/28 GO Bonds | Street Improvements |  | Seal Coat Street Pavement Improvements | Washington Ave (S 3rd St to S 4th St) S 4th St (Walnut to East End) | Planning | 750000 |  |  |  |  | 2027/28 | 2027/28 |  |  | 2028/29 | [5 empty] | No | [7 empty] | 0 | 0 | 750000 |  |  | No | 1
2027/28 | 388 | 2027/28 GO Bonds | Street Improvements | 388- | Asphalt Street Pavement Improvements | Truman Place Regency Court Onyx Street Southdale Drive Clemens Boulevard (S. Dakota Ave to Wilder Ave) | Planning | 4500000 |  |  |  |  | 2027/28 | 2027/28 |  |  | 2028/29 | [5 empty] | No | [7 empty] | 0 | 0 | 4500000 |  |  | No | 1
2027/28 | 388 | 2027/28 GO Bonds | Street Improvements | 388- | Arterial Street Pavement Improvements | Duff Ave (6th St to 13th St) | Planning | 1105000 |  |  |  |  | 2027/28 | 2027/28 |  |  | 2028/29 | [5 empty] | No | [7 empty] | 0 | 0 | 1105000 |  |  | No | 1
2027/28 | 388 | 2027/28 GO Bonds | Street Improvements |  | Cyride Route Pavement Improvements | Bloomington Road (Hoover Ave to Eisenhower Ave) | Planning | 1600000 |  |  |  |  | 2027/28 | 2027/28 |  |  | 2028/29 | [5 empty] | No | [7 empty] | 0 | 0 | 1600000 |  |  | No | 1
2027/28 | 388 | 2027/28 GO Bonds | Street Improvements |  | Alley Pavement Improvement Program | Alley south of Lincoln Way (Washington Ave to S. Walnut Ave) | Planning | 400000 |  |  |  |  | 2027/28 | 2027/28 |  |  | 2027/28 | [5 empty] | No | [7 empty] | 0 | 0 | 400000 |  |  | No | 1
2027/28 | 389 | 2028/29 GO Bonds | Street Improvements |  | Alley Pavement Improvement Program | Alley south of Lincoln Way (S. Duff to S. Sherman Ave) | Planning | 400000 |  |  |  |  | 2027/28 | 2027/28 |  |  | 2028/29 | [5 empty] | No | [7 empty] | 0 | 0 | 400000 |  |  | No | 1
2027/28 | 388 | 2027/28 GO Bonds | Street Improvements |  | Concrete Pavement Improvements | 6th St (Clark Ave to Duff Ave) | Planning | 1300000 |  |  |  |  | 2027/28 | 2027/28 |  |  | 2028/29 | [5 empty] | No | [7 empty] | 0 | 0 | 1300000 |  |  | No | 1
2027/28 | 60 | Road Use Tax | Street Improvements | 060- | Right-of-Way Restoration | City-Wide | Planning | 125000 |  | Dean | 0 |  | 2027/28 | 2027/28 |  |  | 2027/28 | [13 empty] | 0 | 0 | 125000 |  |  |  | 0
2027/28 | 510 | Water Utility | Water Distribution | 510- | Right-of-Way Restoration | City-Wide | Planning | 75000 |  | Dean | 0 |  | 2027/28 | 2027/28 |  |  | 2027/28 | [13 empty] | 0 | 0 | 75000 |  |  |  | 0
2027/28 | 510 | Water Utility | Stormwater | 510- | Well Water Main Protection | South Skunk River (various locations between South East 16th Street and East Lincoln Way) | Planning | 600000 |  |  |  |  | 2027/28 | 2027/28 |  |  | 2028/29 | [5 empty] | No | [7 empty] | 0 | 0 | 600000 |  |  | No | 1
2027/28 | 560 | Stormwater Utility | Stormwater |  | Stormwater Erosion Control Program | Dayton Ave (east side ditch along USDA facility) and Worrell Creek (Ames Airport) | Planning | 750000 |  |  |  |  | 2027/28 | 2027/28 |  |  | 2028/29 | [5 empty] | No | [7 empty] | 0 | 0 | 750000 |  |  | No | 1
2028/29 | 560 | Stormwater Utility | Stormwater | 560- | Right-of-Way Restoration | City-Wide | Planning | 50000 |  | Dean | 0 |  | 2028/29 | 2028/29 |  |  | 2028/29 | [13 empty] | 0 | 0 | 50000 |  |  |  | 0
2028/29 | 520 | Sewer Utility | Sanitary Sewer System | 520- | Right-of-Way Restoration | City-Wide | Planning | 75000 |  | Dean | 0 |  | 2028/29 | 2028/29 |  |  | 2028/29 | [13 empty] | 0 | 0 | 75000 |  |  |  | 0
2028/29 | 60 | Road Use Tax | Street Rehabilitation | 060-7770-439 | Neighborhood Curb Replacement Program | South Franklin Ave (Lincoln Way to Tripp St) Village Dr | Planning | 150000 |  |  |  |  | 2028/29 | 2028/29 |  |  | 2029/30 | [5 empty] | No | [7 empty] | 0 | 0 | 150000 |  |  | No | 0
2028/29 | 389 | 2028/29 GO Bonds | Street Improvements |  | Seal Coat Street Pavement Improvements | South Franklin Ave (Lincoln Way to Tripp St) Village Dr | Planning | 1000000 |  |  |  |  | 2028/29 | 2028/29 |  |  | 2029/30 | [5 empty] | No | [7 empty] | 0 | 0 | 1000000 |  |  | No | 1
2028/29 |  | #N/A | Street Rehabilitation |  | Lincoln Way Bridge Replacement | Lincoln Way Bridge over Ioway Creek | Planning | 1250000 |  |  |  |  | 2028/29 | 2028/29 |  |  | 2029/30 | [5 empty] | No | [7 empty] | 0 | 0 | 1250000 |  |  | No | 1
2028/29 | 389 | 2028/29 GO Bonds | Street Improvements | 389- | Asphalt Street Pavement Improvements | Dickinson Ave (Mortensen Ave s. through circle) Green Hills Dr (Oakwood Rd to Red Oak Dr) Red Oak Drive/Circle White Oak Drive/Circle Burr Oak Circle Jefferson Street/Circle Garner Ave/Circle Nixon Ave/Circle | Planning | 3000000 |  |  |  |  | 2028/29 | 2028/29 |  |  | 2029/30 | [5 empty] | No | [7 empty] | 0 | 0 | 3000000 |  |  | No | 1
2028/29 | 389 | 2028/29 GO Bonds | Street Improvements |  | Concrete Pavement Improvements | 7th St (Grand Ave to Burnett Ave) | Planning | 3600000 |  |  |  |  | 2028/29 | 2028/29 |  |  | 2027/28 | [5 empty] | No | [7 empty] | 0 | 0 | 3600000 |  |  | No | 1
2028/29 | 389 | 2028/29 GO Bonds | Street Improvements |  | Cyride Route Pavement Improvements | 16th Street (Grand Ave to Ridgewood Ave) | Planning | 2400000 |  |  |  |  | 2028/29 | 2028/29 |  |  | 2029/30 | [5 empty] | No | [7 empty] | 0 | 0 | 2400000 |  |  | No | 1
2028/29 | 510 | Water Utility | Water Distribution | 510- | Water System Improvements | Duff Ave (20th St to Northwood Dr) | Planning | 75000 |  |  |  |  | 2028/29 | 2028/29 |  |  | 2029/30 | [13 empty] | 0 | 0 | 75000
2028/29 | 389 | 2028/29 GO Bonds | Street Improvements | 389- | Arterial Street Pavement Improvements | Duff Ave (20th St to Northwood Dr) | Planning | 800000 |  |  |  |  | 2028/29 | 2028/29 |  |  | 2029/30 |  |  |  |  | Yes | Yes | [5 empty] | 300000 |  | 300000 | 300000 | 500000 |  |  | No | 1
2028/29 | 320 | Street Construction | Street Improvements | 320- | Arterial Street Pavement Improvements | Duff Ave (20th St to Northwood Dr) | Planning | 1760000 |  |  |  |  | 2028/29 | 2028/29 |  |  | 2029/30 | [13 empty] | 0 | 0 | 1760000
2028/29 | 60 | Road Use Tax | Street Improvements | 060- | Right-of-Way Restoration | City-Wide | Planning | 125000 |  | Dean | 0 |  | 2028/29 | 2028/29 |  |  | 2029/30 | [13 empty] | 0 | 0 | 125000 |  |  |  | 0
2028/29 | 510 | Water Utility | Water Distribution | 510- | Right-of-Way Restoration | City-Wide | Planning | 75000 |  | Dean | 0 |  | 2028/29 | 2028/29 |  |  | 2029/30 | [13 empty] | 0 | 0 | 75000 |  |  |  | 0
2028/29 | 560 | Stormwater Utility | Stormwater |  | Stormwater Erosion Control Program | Clear Creek bank stabilization and restoration (former Sands McDorman property) | Planning | 1400000 |  |  |  |  | 2028/29 | 2028/29 |  |  | 2029/30 | [5 empty] | No | [7 empty] | 0 | 0 | 1400000 |  |  | No | 1
2029/30 | 388 | 2027/28 GO Bonds | Street Improvements | 388- | Arterial Street Pavement Improvements | E. 13th St (McCormick Ave to Dayton Ave) | Planning | 2400000 |  |  |  |  | 2029/30 | 2029/30 |  |  | 2030/31 |  |  |  |  | Yes | Yes | [7 empty] | 0 | 0 | 2400000 |  |  | Yes | 1
2029/30 | 320 | Street Construction | Street Improvements | 320- | Arterial Street Pavement Improvements | E. 13th St (McComick Ave to Dayton Ave) | Planning | 1835000 |  |  |  |  | 2029/30 | 2029/30 |  |  | 2030/31 | [13 empty] | 0 | 0 | 1835000 |  |  |  | 1
2029/30 | 560 | Stormwater Utility | Stormwater | 560- | Right-of-Way Restoration | City-Wide | Planning | 50000 |  | Dean | 0 |  | 2029/30 | 2029/30 |  |  | 2030/31 | [13 empty] | 0 | 0 | 50000 |  |  |  | 0
2029/30 | 520 | Sewer Utility | Sanitary Sewer System | 520- | Right-of-Way Restoration | City-Wide | Planning | 75000 |  | Dean | 0 |  | 2029/30 | 2029/30 |  |  | 2030/31 | [13 empty] | 0 | 0 | 75000 |  |  |  | 0
2029/30 |  | #N/A |  |  | Bridge Rehabilitation Program | Lincoln Way Bridge over Ioway Creek | Planning | [5 empty] | 2029/30 | 2029/30 |  |  | 2030/31 | [5 empty] | No | [7 empty] | 0 | 0 | 0 |  |  | No | 0
2029/30 | 390 | 2029/30 GO Bonds | Street Improvements | 390- | Asphalt Street Pavement Improvements | Roosevelt (16th St to 20th St) Cessna St Woodland (Franklin Ave to Hira Park) Wilder Blvd (170' north of Rowling Dr to Lincoln Way) | Planning | 3700000 |  |  |  |  | 2029/30 | 2029/30 |  |  | 2030/31 | [5 empty] | No | [7 empty] | 0 | 0 | 3700000 |  |  | No | 1
2029/30 | 389 | 2028/29 GO Bonds | Street Improvements |  | Cyride Route Pavement Improvements | Dickinson Ave (Mortensen Rd to Steinbeck St) Steinbeck St (S Dakota Ave to Poe Ave) | Planning | [5 empty] | 2029/30 | 2029/30 |  |  | 2030/31 | [5 empty] | No | [7 empty] | 0 | 0 | 0 |  |  | No | 1
2029/30 | 390 | 2029/30 GO Bonds | Street Improvements |  | Alley Pavement Improvement Program | Alley south of Lincon Way (S. Kellogg Ave to Washington Ave) | Planning | 400000 |  |  |  |  | 2029/30 | 2029/30 |  |  | 2030/31 | [5 empty] | No | [7 empty] | 0 | 0 | 400000 |  |  | No | 1
2029/30 | 390 | 2029/30 GO Bonds | Street Improvements |  | Concrete Pavement Improvements | 13th Street (Hyland Ave to Union Pacific RR Bridge) | Planning | 900000 |  |  |  |  | 2029/30 | 2029/30 |  |  | 2030/31 | [5 empty] | No | [7 empty] | 0 | 0 | 900000 |  |  | No | 1
2029/30 | 60 | Road Use Tax | Street Rehabilitation | 060-7770-439 | Neighborhood Curb Replacement Program | Country Club (Cessna to Pearson) | Planning | 150000 |  |  |  |  | 2029/30 | 2029/30 |  |  | 2030/31 | [5 empty] | No | [7 empty] | 0 | 0 | 150000 |  |  | No | 0
2029/30 | 390 | 2029/30 GO Bonds | Street Improvements |  | Seal Coat Street Pavement Improvements | Country Club (Cessna to Pearson) | Planning | 1000000 |  |  |  |  | 2029/30 | 2029/30 |  |  | 2030/31 | [5 empty] | No | [7 empty] | 0 | 0 | 1000000 |  |  | No | 1
2029/30 | 390 | 2029/30 GO Bonds | Street Improvements | 390- | Arterial Street Pavement Improvements | E. 13th St (between ramps under I35) E Lincoln Way/Dayton Ave Intersection | Planning | 486000 |  |  |  |  | 2029/30 | 2029/30 |  |  | 2030/31 | [5 empty] | No | [7 empty] | 0 | 0 | 486000 |  |  | No | 1
2029/30 | 320 | Street Construction | Street Improvements | 320- | Arterial Street Pavement Improvements | E. 13th St (between ramps under I35) E Lincoln Way/Dayton Ave Intersection | Planning | 864000 |  |  |  |  | 2029/30 | 2029/30 |  |  | 2030/31 |  |  |  |  | Yes | Yes | [7 empty] | 0 | 0 | 864000 |  |  |  | 0
2029/30 | 60 | Road Use Tax | Street Improvements | 060- | Right-of-Way Restoration | City-Wide | Planning | 125000 |  | Dean | 0 |  | 2029/30 | 2029/30 |  |  | 2030/31 | [13 empty] | 0 | 0 | 125000 |  |  |  | 0
2029/30 | 510 | Water Utility | Water Distribution | 510- | Right-of-Way Restoration | City-Wide | Planning | 75000 |  | Dean | 0 |  | 2029/30 | 2029/30 |  |  | 2030/31 | [13 empty] | 0 | 0 | 75000 |  |  |  | 0
2029/30 | 560 | Stormwater Utility | Stormwater |  | Stormwater Erosion Control Program | Ioway Creek in Stuart Smith Park | Planning | [5 empty] | 2029/30 | 2029/30 |  |  | 2030/31 | [5 empty] | No | [7 empty] | 0 | 0 | 0 |  |  | No | 1
2030/31 | 387 | 2026/27 GO Bonds | Street Improvements |  | Campustown Public Improvements | Chamberlain St (Hayward Ave to Lynn Ave) | Planning | 1400000 |  |  |  |  | 2030/31 | 2030/31 |  |  | 2031/32 | [5 empty] | No | [7 empty] | 0 | 0 | 1400000 |  |  | No | 1
2030/31 | 560 | Stormwater Utility | Stormwater | 560- | Low Point Drainage Improvements | Hoover Ave and Adams St Intersection | Planning | [5 empty] | 2030/31 | 2030/31 |  | 2031/32 | [14 empty] | 0 | 0 | 0 |  |  |  | 1
2030/31 | 560 | Stormwater Utility | Stormwater | 560- | Low Point Drainage Improvements | 3711 and 3719 Hoover Ave | Planning | [5 empty] | 2030/31 | 2030/31 |  | 2031/32 | [14 empty] | 0 | 0 | 0 |  |  |  | 1
2030/31 | 560 | Stormwater Utility | Stormwater | 560- | Right-of-Way Restoration | City-Wide | Planning | 50000 |  | Dean | 0 |  | 2030/31 | 2030/31 |  | 2031/32 | [14 empty] | 0 | 0 | 50000 |  |  |  | 0
2030/31 | 520 | Sewer Utility | Sanitary Sewer System | 520- | Right-of-Way Restoration | City-Wide | Planning | 75000 |  | Dean | 0 |  | 2030/31 | 2030/31 |  | 2031/32 | [14 empty] | 0 | 0 | 75000 |  |  |  | 0
2030/31 | 391 | 2030/31 GO Bonds | Street Improvements | 391- | Concrete Pavement Improvements | 7th St (Burnett to Duff) | Planning | 1200000 |  |  |  |  | 2030/31 | 2030/31 |  | 2031/32 | [12 empty] | 600000 |  | 600000 | 600000 | 600000 |  |  |  | 1
2030/31 | 391 | 2030/31 GO Bonds | Street Improvements | 391- | Cyride Route Pavement Improvements | Thackery Ave (Todd Dr to Lincoln Way) Todd Dr (Thackeray to Alcott) Alcott Ave (Todd Dr to Lincoln Way) | Planning | 1700000 |  |  |  |  | 2030/31 | 2030/31 |  | 2031/32 | [12 empty] | 340000
2030/31 | 391 | 2030/31 GO Bonds | Street Improvements | 391- | Arterial Street Pavement Improvements | E. 13th St (250' East of Meadowlane Ave to Skunk River) | Planning | 460000 |  |  |  |  | 2030/31 | 2030/31 |  | 2031/32 | [12 empty] | 380000 |  | 380000 | 380000 | 80000 |  |  |  | 1
2030/31 | 320 | Street Construction | Street Improvements | 320- | Arterial Street Pavement Improvements | E. 13th St (250' East of Meadowlane Ave to Skunk River) | Planning | 2160000 |  |  |  |  | 2030/31 | 2030/31 |  | 2031/32 | [14 empty] | 0 | 0 | 2160000 |  |  |  | 0
2030/31 | 391 | 2030/31 GO Bonds | Street Improvements | 391- | Alley Pavement Improvement Program | Alley between Douglas Ave and Duff Ave (7th St to 8th St) | Planning | 400000 |  |  |  |  | 2030/31 | 2030/31 |  | 2031/32 | [14 empty] | 0 | 0 | 400000 |  |  |  | 1
2030/31 | 30 | Local Option Sales Tax | Shared Use Paths | 030- | Shared Use Path Extension | E. 13th St (250' East of Meadowlane Ave to Skunk River) | Planning | 80000 |  |  |  |  | 2030/31 | 2030/31 |  | 2031/32 | [14 empty] | 0 | 0 | 80000 |  |  |  | 0
2030/31 | 391 | 2030/31 GO Bonds | Street Improvements | 391- | Asphalt Street Pavement Improvements | Stone Brooke Road (Fletcher to Fletcher) Stone Brooke Circle Douglas Ave (O'Neil to Duff) O'Neil Dr (Douglas to Duff) | Planning | [5 empty] | 2030/31 | 2030/31 |  | 2031/32 | [14 empty] | 0 | 0 | 0 |  |  |  | 1
2030/31 | 60 | Road Use Tax | Street Improvements | 060- | Right-of-Way Restoration | City-Wide | Planning | 125000 |  | Dean | 0 |  | 2030/31 | 2030/31 |  | 2031/32 | [14 empty] | 0 | 0 | 125000 |  |  |  | 0
2030/31 | 510 | Water Utility | Water Distribution | 510- | Right-of-Way Restoration | City-Wide | Planning | 75000 |  | Dean | 0 |  | 2030/31 | 2030/31 |  | 2031/32 | [14 empty] | 0 | 0 | 75000 |  |  |  | 0
2030/31 | 391 | 2030/31 GO Bonds | Street Improvements | 391- | Seal Coat Street Pavement Improvements | Pearson Ave (Country Club to Sunset Dr) Greeley St (Pearson Ave to Beach Ave) | Planning | [5 empty] | 2030/31 | 2030/31 |  | 2031/32 | [14 empty] | 0 | 0 | 0 |  |  |  | 1
2031/32 | 520 | Sewer Utility | Sanitary Sewer System | 520- | Sanitary Sewer System Improvements | 7th St (Northwestern-Grand) Wilson Ave (7th - 13th) Hodge Ave (6th - 7th) | Planning | 200000 |  |  |  |  | 2031/32 | 2031/32 |  | 2032/33 | [14 empty] | 0 | 0 | 200000
2031/32 | 392 | 2031/32 GO Bonds | Street Improvements | 392- | Alley Pavement Improvement Program | Alley between Douglas Ave and Duff Ave (8th S to 9th St) | Planning | 400000 |  |  |  |  | 2031/32 | 2031/32 |  | 2032/33 | [14 empty] | 0 | 0 | 400000 |  |  |  | 1
2031/32 | 392 | 2031/32 GO Bonds | Street Improvements | 392- | Arterial Street Pavement Improvements | Lincoln Highway and County Line Road Roundabout | Planning | 520000 |  |  |  |  | 2031/32 | 2031/32 |  | 2032/33 | [14 empty] | 0 | 0 | 520000 |  |  |  | 1
2031/32 | 320 | Street Construction | Street Improvements | 320- | Arterial Street Pavement Improvements | Lincoln Highway and County Line Road Roundabout | Planning | 2080000 |  |  |  |  | 2031/32 | 2031/32 |  | 2032/33 | [14 empty] | 0 | 0 | 2080000 |  |  |  | 1
2031/32 | 392 | 2031/32 GO Bonds | Street Improvements | 392- | Concrete Pavement Improvements | 7th St (Northwestern-Grand) Wilson Ave (7th - 13th) Hodge Ave (6th - 7th) | Planning | 3400000 |  |  |  |  | 2031/32 | 2031/32 |  | 2032/33 | [14 empty] | 0 | 0 | 3400000 |  |  |  | 1
2031/32 | 510 | Water Utility | Water Distribution | 510- | Water System Improvements | 7th St (Northwestern-Grand) Wilson Ave (7th - 13th) Hodge Ave (6th - 7th) | Planning | 200000 |  |  |  |  | 2031/32 | 2031/32 |  | 2032/33 | [14 empty] | 0 | 0 | 200000
2032/33 | 393 | 2032/33 GO Bonds | Street Improvements |  | Alley Pavement Improvement Program | Alley between Douglas Ave and Duff Ave (6th St to 7th St) | Planning | 400000 |  |  |  |  | 2032/33 | 2032/33 |  | 2033/37 | [14 empty] | 0 | 0 | 400000 |  |  |  | 1
2025/26 | 386 | 2025/26 GO Bonds | Street Improvements | 386-8159-439 | Concrete Pavement Improvements | Clark Ave (9th St to 13th St) | Design | 1250000 |  | WHKS | 0 | 0 | 2025/26 | 2025/26 |  |  | 2026/27 | 2027-06-30 |  | Dean |  | No | No | 1085116.6 |  |  |  |  | 150000 |  | 1235116.6 | 150000 | 14883.4 |  |  |  | 1
Note on AB90: Bryngelson, Mindy: San. Service
Note on AB103: Bryngelson, Mindy: Internal plumbing not working properly. Seems new water pressure has scaled pipes and now some units are clogged and have no water. Draintech to complete work.
Note on AB104: Bryngelson, Mindy: Landscape Repair

## 2025-26 CIP Costs
Row Labels | Sum of Overall Budget | CIP | Difference
2025/26 | 16303000 | 16050000 | -253000
Alley Pavement Improvement Program | 400000 | 400000 | 0
Asphalt Street Pavement Improvements | 4000000 | 4000000 | 0
Clear Water Diversion | 53000 | 50000 | -3000 | ok, will use fund balance
Collector Street Pavement Improvements | 1200000 | 1200000 | 0
Concrete Pavement Improvements | 3800000 | 3800000 | 0
Downtown Street Improvements | 250000 | 250000 | 0
Low Point Drainage Improvements | 500000 | 500000 | 0
Neighborhood Curb Replacement Program | 150000 | 150000 | 0
Right-of-Way Restoration | 325000 | 325000 | 0
Sanitary Sewer System Improvements | 743000 | 350000 | -393000 | ok - includes $400,000 for Hwy 30
Seal Coat Street Pavement Improvements | 1000000 | 1000000 | 0
Shared Use Path Maintenance | 100000 | 375000 | 275000
Stormwater Erosion Control Program | 850000 | 850000 | 0 | defer Canterbury
Stormwater Improvement Program | 380000 | 650000 | 270000
Stormwater Quality Improvements | 100000 | 100000 | 0
Water System Improvements | 2452000 | 2050000 | -402000 | ok, will use fund balance
Grand Total | 16303000
Fiscal Year | 2025/26
2025/26 CIP Projects | CIP Budget | PSA Costs | Construction Costs | COA Est Costs | Total Est Costs | Budget - Est Costs | Notes
25/26 Sanitary and Storm Televising | 50000 | 0 | 49942.46 | 0 | 49942.46 | 57.54
Stormwater Improvement Program | 50000 | 0 | 49942.46 | 0 | 49942.46 | 57.54
560-8642-489 | 50000 | 0 | 49942.46 | 0 | 49942.46 | 57.54
6th St / Duff Ave 20th St / Northwestern Ave S Bell Ave / SE 16th St Grove Ave / River Oak Dr | 500000 | 0 |  |  | 0 | 500000
Low Point Drainage Improvements | 500000 | 0 |  |  | 0 | 500000
560-8659-489 | 500000 | 0 |  |  | 0 | 500000
Alley south of Lincoln Way (S. Kellogg Ave to Sherman Ave) | 400000 | 0 | 160000 | 21400 | 181400 | 218600
Alley Pavement Improvement Program | 400000 | 0 | 160000 | 21400 | 181400 | 218600
386-8172-439 | 400000 | 0 | 160000 | 21400 | 181400 | 218600
Bloomington Road (GW Carver to Eisenhower Ave) | 1300000 | 72000 | 1057386.5 | 123000 | 1252386.5 | 47613.5
Collector Street Pavement Improvements | 1200000 | 72000 | 954015.5 | 123000 | 1149015.5 | 50984.5
320-8133-439 | 700000 | 0 | 700000 | 0 | 700000 | 0
386-8133-439 | 500000 | 72000 | 254015.5 | 123000 | 449015.5 | 50984.5
Shared Use Path Maintenance | 100000 | 0 | 103371 | 0 | 103371 | -3371
030-881-439 | 100000 | 0 | 103371 | 0 | 103371 | -3371 | May need to pull from fund balance.
City-Wide | 325000 | 0 | 165000 | 160000 | 325000 | 0
Right-of-Way Restoration | 325000 | 0 | 165000 | 160000 | 325000 | 0
510- | 75000 | 0 | 35000 | 40000 | 75000 | 0 | Will pull from fund balance ($90,147 on 10/2/2025)
520- | 75000 | 0 | 35000 | 40000 | 75000 | 0
560- | 50000 | 0 | 10000 | 40000 | 50000 | 0
060-8194-439 | 125000 | 0 | 85000 | 40000 | 125000 | 0
East/West alley north of Lincoln Way (Sherman Ave to Kellogg Ave) | 250000 | 0 | 180000 | 24000 | 204000 | 46000
Downtown Street Improvements | 250000 | 0 | 180000 | 24000 | 204000 | 46000
383-8150-439 | 250000 | 0 | 180000 | 24000 | 204000 | 46000
Ferndale Ave (20th St to 24th St) Furman Drive | 1830000 | 0 | 2802834 | 200000 | 3002834 | -1172834
Neighborhood Curb Replacement Program | 150000 | 0 | 330959 | 0 | 330959 | -180959
060-7770-439 | 150000 | 0 | 330959 | 0 | 330959 | -180959 | On Hold - No funding at this time.
Seal Coat Street Pavement Improvements | 1000000 | 0 | 1884000 | 200000 | 2084000 | -1084000
386-8101-489 | 1000000 | 0 | 1884000 | 200000 | 2084000 | -1084000
Water System Improvements | 680000 | 0 | 587875 | 0 | 587875 | 92125
510-8461-489 | 680000 | 0 | 587875 | 0 | 587875 | 92125
Grand & 13th Intersection | 758000 | 0 | 758000 | 0 | 758000 | 0
Sanitary Sewer System Improvements | 68000 | 0 | 68000 | 0 | 68000 | 0
520-7525-489 | 68000 | 0 | 68000 | 0 | 68000 | 0
Water System Improvements | 690000 | 0 | 690000 | 0 | 690000 | 0
510-7525-489 | 690000 | 0 | 690000 | 0 | 690000 | 0
Highway 30 Sanitary Sewer Relocation | 400000 | 14000 | 350000 | 14000 | 378000 | 22000
Sanitary Sewer System Improvements | 400000 | 14000 | 350000 | 14000 | 378000 | 22000
520-8521-489 | 400000 | 14000 | 350000 | 14000 | 378000 | 22000
Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | 4390000 | 302000 | 3677000 | 300000 | 4279000 | 111000
Asphalt Street Pavement Improvements | 4000000 | 302000 | 3340000 | 300000 | 3942000 | 58000 | Will pull from fund balance ($481,421 on 10/2/2025)
386-8118-489 | 4000000 | 302000 | 3340000 | 300000 | 3942000 | 58000
Sanitary Sewer System Improvements | 100000 | 0 | 80000 | 0 | 80000 | 20000 | Will setup alternates
520-8118-489 | 100000 | 0 | 80000 | 0 | 80000 | 20000
Stormwater Improvement Program | 60000 | 0 | 57000 | 0 | 57000 | 3000
560-8118-489 | 60000 | 0 | 57000 | 0 | 57000 | 3000
Water System Improvements | 230000 | 0 | 200000 | 0 | 200000 | 30000
510-8118-489 | 230000 | 0 | 200000 | 0 | 200000 | 30000
Moore Memorial Park Sanitary Sewer Lining | 0 | 13400 | 148640 | 15000 | 177040 | -177040
Sanitary Sewer System Improvements | 0 | 13400 | 148640 | 15000 | 177040 | -177040
520-8542-489 | 0 | 13400 | 148640 | 15000 | 177040 | -177040 | Pulled from fund balance - unplanned project.
Sunset Drive (Ash Ave to Beach Ave) | 1805000 | 0 | 1652812.13 | 130000 | 1782812.13 | 22187.87
Concrete Pavement Improvements | 1100000 | 0 | 958272.13 | 130000 | 1088272.13 | 11727.87
386-8161-439 | 1100000 | 0 | 958272.13 | 130000 | 1088272.13 | 11727.87
Sanitary Sewer System Improvements | 95000 | 0 | 93000 | 0 | 93000 | 2000
520-8161-489 | 95000 | 0 | 93000 | 0 | 93000 | 2000
Stormwater Improvement Program | 270000 | 0 | 268050 | 0 | 268050 | 1950
560-8161-489 | 270000 | 0 | 268050 | 0 | 268050 | 1950
Water System Improvements | 340000 | 0 | 333490 | 0 | 333490 | 6510
510-8161-489 | 340000 | 0 | 333490 | 0 | 333490 | 6510
Worrell Creek Bank Stabilization (south of Mortensen Pkwy from Gateway Hill Park Dr to University Blvd) | 850000 | 90000 | 670000 | 90000 | 850000 | 0
Stormwater Erosion Control Program | 850000 | 90000 | 670000 | 90000 | 850000 | 0
560-8634-489 | 850000 | 90000 | 670000 | 90000 | 850000 | 0 | Will pull from fund balance - unplanned project.
Animal Shelter Site | 100000 |  |  |  | 0 | 100000
Stormwater Quality Improvements | 100000 |  |  |  | 0 | 100000
560-8601-489 | 100000 |  |  |  | 0 | 100000
Campus Ave (Lincoln Way to Oakland St) | 1530000 | 321000 | 1033567.75 | 129000 | 1483567.75 | 46432.25
Concrete Pavement Improvements | 1450000 | 321000 | 963667.75 | 129000 | 1413667.75 | 36332.25
386-8160-439 | 1450000 | 321000 | 963667.75 | 129000 | 1413667.75 | 36332.25
Sanitary Sewer System Improvements | 80000 | 0 | 69900 | 0 | 69900 | 10100
520-8160-489 | 80000 | 0 | 69900 | 0 | 69900 | 10100
Clark Ave (9th St to 13th St) | 1815000 | 0 | 1648991.6 | 150000 | 1798991.6 | 16008.4
Clear Water Diversion | 53000 | 0 | 52500 | 0 | 52500 | 500
520-8159-489 | 53000 | 0 | 52500 | 0 | 52500 | 500
Concrete Pavement Improvements | 1250000 | 0 | 1085116.6 | 150000 | 1235116.6 | 14883.4 | No project planned
386-8159-439 | 1250000 | 0 | 1085116.6 | 150000 | 1235116.6 | 14883.4
Water System Improvements | 512000 | 0 | 511375 | 0 | 511375 | 625
510-8159-489 | 512000 | 0 | 511375 | 0 | 511375 | 625
Grand Total | 16303000 | 812400 | 14354174.44 | 1356400 | 16522974.44 | -219974.44

## COA Salary Staff Time
Fiscal Year Journaled | Project Name | Fund | Account # | Journaled this FY | Remaining for next FY | Notes | Target 89% | Row Labels | Sum of Journaled this FY | Journal Entry Target 89% | Sum of Differnce
2024/25 | CIP Salary Allocation | [5 empty] | 1585438.88 | 2024/25 | 1180077.17 | 1585438.88 | 405361.71
2024/25 | ROW Restoration - Water | 510 | 510-8194-439 | 32895.6 | 0 |  |  | 2025/26 | 610881 | 1585438.88 | 974557.88
2024/25 | Sanitary Sewer Rehab | 520 | 520-8542-489 | 100000 | 0 |  |  | Grand Total | 1790958.17 | 3170877.76 | 1379919.59
2024/25 | ROW Restoration - Stormwater | 560 | 560-8194-439 | 22857 | 0
2024/25 | Airport Road | 384 | 384-8143-439 | 140000 | 0
2024/25 | E 16th St, Glendale, Quebec | 384 | 384-8101-439 | 130000 | 0
2024/25 | Clear Water Diversion | 520 | 520-8585-489 | 12000 | 0
2024/25 | 24th & Stange | 382 | 382-8167-439 | 140000 | 0
2024/25 | College Creek Bank Stabilization (Hemingway Drive) | 560 | 560-8639-489 | 10000 | 10000
2024/25 | Low Point Drainage Improvemenets | 560 | 560-8659-489 | 10000 | 20000
2024/25 | Cyride (Lincoln Way) | 383 | 383-8122-489 | 100000 | 0
2024/25 | 6th St (Brookridge Ave to Northwestern Ave) | 384 | 384-8131-439 | 100000 | 100000
2024/25 | Oakland St. (Hawthorne Ave to Franklin Ave) | 381 | 381-8132-439 | 50000 | 50000 | 381, 382, or 383 Accounts
2024/25 | Concrete (Brookridge, etc.) | 383 | 383-8168-439 | 145000 | 0
2024/25 | Bloomington Waterway (Hyde Ave to Harrison Road) | 560 | 560-8637-489 | 2324.57
2024/25 | Prairie View (East Industrial) |  |  | 120000 | 0
2024/25 | ROW Restoration - Road Use Tax | 60 | 060-8194-439 | 45000 | 0
2024/25 | Ioway Creek | 560 | 560-8636-489 | 20000 | 82080
2024/25
2024/25
2024/25
2024/25
2024/25
2024/25
2024/25
2024/25
2024/25
2025/26 | CIP Salary Allocation | [5 empty] | 1585438.88
2025/26 | Prairie View West: Prairie View East | 384 | 384-8169-439 | 250000 | 0 | place all in 2025/26
2025/26 | College Creek Bank Stabilization (Hemingway Drive) | 560 | 560-8639-489 | 10000 | 0
2025/26 | Low Point Drainage Improvemenets | 560 | 560-8659-489 | 20000 | 0
2025/26 | 6th St (Brookridge Ave to Northwestern Ave) | 384 | 384-8131-439 | 100000 | 0
2025/26 | Oakland St. (Oliver Ave to Hawthorne Ave) | 382 | 382-8132-439 | 100000 | 0
2025/26 | S 16th St Roadway Widening | 320 | 320-8183-439 | 73875 | 73875
2025/26 | 550th (Ken Maril Rd to 265th St) | 520 | 520-8572-489 | 32006 |  | place all in 2025/26
2025/26 | Ada Hayden Trail (parks) |  |  | 25000
2025/26 | Ioway Creek | 560 | 560-8636-489 | 0

## Current Active Projects
Current Phase | (Multiple Items)
Row Labels | Sum of Overall Budget | Row Labels | Sum of Overall Budget
2018/19 | 654000 | Bidding | 400000
Stormwater | 654000 | Sanitary Sewer System | 400000
South Skunk River (various locations between South East 16th Street and East Lincoln Way) | 654000 | Highway 30 Sanitary Sewer Relocation | 400000
2019/20 | 2158000 | Close-Out | 4092601.46
Stormwater | 2158000 | Sanitary Sewer System | 3154121
Ioway Creek (6th St. to 13th St) | 2158000 | S 500th Avenue County Line Road | 654121
2021/22 | 130091 | Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | 200000
Stormwater | 130091 | E 13th St (S. Dayton Ave to East of I-35) | 2300000
Northridge Heights Pond on GW Carver | 130091 | Stormwater | 130091
2022/23 | 8343486 | Northridge Heights Pond on GW Carver | 130091
Sanitary Sewer System | 7462240 | ROW Restoration
Basin 11 | 2100000 | Water Distribution | 808389.46
Downtown (Basin 12) | 2336322 | Kellogg Ave (7th St. to 13th St) 11th St (Burnett Ave to Kellogg Ave) | 808389.46
E 13th St (S. Dayton Ave to East of I-35) | 2300000 | Construction | 12024404
US 69 (Basin 12) | 725918 | Sanitary Sewer System | 55500
Stormwater | 881246 | 6th St (Brookridge Ave to Northwestern Ave) | 35000
1100 Kennedy St East Lincoln Way (2000 block) 2100/2200 Jensen Ave Barr Drive Pearle Ave Alley Harrison Road (1900 block) Northridge Lane (2800 block) Garnet Dr (700 block) Idaho Ct (1200 block) | 632146 | Hyland Ave (Lincoln Way to Ontario St) | 20500
Clear Creek bank Stabilization (west of Brittish Columbia Ave) | 249100 | Stormwater | 3040146
2023/24 | 12573447.46 | 1100 Kennedy St East Lincoln Way (2000 block) 2100/2200 Jensen Ave Barr Drive Pearle Ave Alley Harrison Road (1900 block) Northridge Lane (2800 block) Garnet Dr (700 block) Idaho Ct (1200 block) | 632146
Sanitary Sewer System | 8389121 | Ioway Creek (6th St. to 13th St) | 2158000
6th St (Brookridge Ave to Northwestern Ave) | 35000 | S. 16th (University Boulevard to Apple Place) | 250000
S 500th Avenue County Line Road | 654121 | Street Improvements | 6390958
Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | 200000 | 6th St (Brookridge Ave to Northwestern Ave) | 1365300
East Lincoln Way & Nikkol Trunk Line | 7500000 | Hyland Ave (Lincoln Way to Ontario St) | 2620890
Stormwater | 600000 | S. 16th (University Boulevard to Apple Place) | 683937
Inis Grove (near restroom) | 600000 | Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | 982837
Street Improvements | 2348137 | Oakland St. (Oliver Ave to Hawthorne Ave) | 737994
6th St (Brookridge Ave to Northwestern Ave) | 1365300 | Water Distribution | 2537800
Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | 982837 | 6th St (Brookridge Ave to Northwestern Ave) | 28000
Water Distribution | 1236189.46 | S. Riverside (S. 4th St to Lincoln Way) | 700000
6th St (Brookridge Ave to Northwestern Ave) | 28000 | S. Russell (S 4th to Lincoln Way) | 680000
Kellogg Ave (7th St. to 13th St) 11th St (Burnett Ave to Kellogg Ave) | 808389.46 | Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | 399800
Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | 399800 | Oakland St. (Oliver Ave to Hawthorne Ave) | 350000
2024/25 | 8615578 | E. 14th St. (Glendale to Meadowlane) Meadowlane (E. 13th St. to E. 14th St.) | 380000
Sanitary Sewer System | 20500 | Design | 31885597
Hyland Ave (Lincoln Way to Ontario St) | 20500 | Sanitary Sewer System | 13058240
Stormwater | 1242257 | Basin 11 | 2100000
Clear Creek Bank Stablization (west of North Dakota Ave) | 350000 | Downtown (Basin 12) | 2336322
S. 16th (University Boulevard to Apple Place) | 250000 | Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | 100000
Stormwater System Analysis | 642257 | East Lincoln Way & Nikkol Trunk Line | 7500000
ROW Restoration |  | Grand & 13th Intersection | 68000
Street Improvements | 4042821 | Sunset Drive (Ash Ave to Beach Ave) | 95000
Hyland Ave (Lincoln Way to Ontario St) | 2620890 | US 69 (Basin 12) | 725918
S. 16th (University Boulevard to Apple Place) | 683937 | Moore Memorial Park Sanitary Sewer Lining | 0
Oakland St. (Oliver Ave to Hawthorne Ave) | 737994 | Campus Ave (Lincoln Way to Oakland St) | 80000
Water Distribution | 3310000 | Clark Ave (9th St to 13th St) | 53000
Douglas Ave (16th St to 17th St) Barr Drive 17th St (Douglas Ave to West St) | 1200000 | Shared Use Paths | 100000
S. Riverside (S. 4th St to Lincoln Way) | 700000 | Bloomington Road (GW Carver to Eisenhower Ave) | 100000
S. Russell (S 4th to Lincoln Way) | 680000 | Stormwater | 4275357
Oakland St. (Oliver Ave to Hawthorne Ave) | 350000 | 6th St / Duff Ave 20th St / Northwestern Ave S Bell Ave / SE 16th St Grove Ave / River Oak Dr | 500000
E. 14th St. (Glendale to Meadowlane) Meadowlane (E. 13th St. to E. 14th St.) | 380000 | Clear Creek bank Stabilization (west of Brittish Columbia Ave) | 249100
2025/26 | 15928000 | Clear Creek Bank Stablization (west of North Dakota Ave) | 350000
Sanitary Sewer System | 796000 | Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | 60000
Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | 100000 | South Skunk River (various locations between South East 16th Street and East Lincoln Way) | 654000
Grand & 13th Intersection | 68000 | Stormwater System Analysis | 642257
Highway 30 Sanitary Sewer Relocation | 400000 | Worrell Creek Bank Stabilization (south of Mortensen Pkwy from Gateway Hill Park Dr to University Blvd) | 850000
Sunset Drive (Ash Ave to Beach Ave) | 95000 | Sunset Drive (Ash Ave to Beach Ave) | 270000
Moore Memorial Park Sanitary Sewer Lining | 0 | Inis Grove (near restroom) | 600000
Campus Ave (Lincoln Way to Oakland St) | 80000 | Animal Shelter Site | 100000
Clark Ave (9th St to 13th St) | 53000 | Street Improvements | 10650000
Shared Use Paths | 100000 | Alley south of Lincoln Way (S. Kellogg Ave to Sherman Ave) | 400000
Bloomington Road (GW Carver to Eisenhower Ave) | 100000 | Bloomington Road (GW Carver to Eisenhower Ave) | 1200000
Stormwater | 1780000 | East/West alley north of Lincoln Way (Sherman Ave to Kellogg Ave) | 250000
6th St / Duff Ave 20th St / Northwestern Ave S Bell Ave / SE 16th St Grove Ave / River Oak Dr | 500000 | Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | 4000000
Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | 60000 | Ferndale Ave (20th St to 24th St) Furman Drive | 1000000
Worrell Creek Bank Stabilization (south of Mortensen Pkwy from Gateway Hill Park Dr to University Blvd) | 850000 | Sunset Drive (Ash Ave to Beach Ave) | 1100000
Sunset Drive (Ash Ave to Beach Ave) | 270000 | Campus Ave (Lincoln Way to Oakland St) | 1450000
Animal Shelter Site | 100000 | Clark Ave (9th St to 13th St) | 1250000
Street Improvements | 10650000 | Street Rehabilitation | 150000
Alley south of Lincoln Way (S. Kellogg Ave to Sherman Ave) | 400000 | Ferndale Ave (20th St to 24th St) Furman Drive | 150000
Bloomington Road (GW Carver to Eisenhower Ave) | 1200000 | Water Distribution | 3652000
East/West alley north of Lincoln Way (Sherman Ave to Kellogg Ave) | 250000 | Douglas Ave (16th St to 17th St) Barr Drive 17th St (Douglas Ave to West St) | 1200000
Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | 4000000 | Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | 230000
Ferndale Ave (20th St to 24th St) Furman Drive | 1000000 | Ferndale Ave (20th St to 24th St) Furman Drive | 680000
Sunset Drive (Ash Ave to Beach Ave) | 1100000 | Grand & 13th Intersection | 690000
Campus Ave (Lincoln Way to Oakland St) | 1450000 | Sunset Drive (Ash Ave to Beach Ave) | 340000
Clark Ave (9th St to 13th St) | 1250000 | Clark Ave (9th St to 13th St) | 512000
Street Rehabilitation | 150000 | Grand Total | 48402602.46
Ferndale Ave (20th St to 24th St) Furman Drive | 150000
Water Distribution | 2452000
Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | 230000
Ferndale Ave (20th St to 24th St) Furman Drive | 680000
Grand & 13th Intersection | 690000
Sunset Drive (Ash Ave to Beach Ave) | 340000
Clark Ave (9th St to 13th St) | 512000
Grand Total | 48402602.46

## Current Construction Projects
Current Phase | (Multiple Items) |  | Current Phase | (Multiple Items)
Row Labels | Sum of Overall Budget | Sum of Bid Amount | Row Labels | Count of Project Name
1100 Kennedy St East Lincoln Way (2000 block) 2100/2200 Jensen Ave Barr Drive Pearle Ave Alley Harrison Road (1900 block) Northridge Lane (2800 block) Garnet Dr (700 block) Idaho Ct (1200 block) | 632146 | 523245.2 | Sanitary Sewer System | 3
Stormwater | 632146 | 523245.2 | Stormwater | 4
6th St (Brookridge Ave to Northwestern Ave) | 1428300 | 1261356 | Street Improvements | 13
Sanitary Sewer System | 35000 | 35000 | Water Distribution | 6
Street Improvements | 1365300 | 1198926 | Grand Total | 26
Water Distribution | 28000 | 27430
Hyland Ave (Lincoln Way to Ontario St) | 2641390 | 2011694.05
Sanitary Sewer System | 20500 | 20500
Street Improvements | 2620890 | 1991194.05
Ioway Creek (6th St. to 13th St) | 2158000 | 1687433
Stormwater | 2158000 | 1687433
S. 16th (University Boulevard to Apple Place) | 933937 | 767926.1
Stormwater | 250000 | 196124
Street Improvements | 683937 | 571802.1
S. Riverside (S. 4th St to Lincoln Way) | 700000 | 559321.3
Water Distribution | 700000 | 559321.3
S. Russell (S 4th to Lincoln Way) | 680000 | 484024.4
Water Distribution | 680000 | 484024.4
Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | 1382637 | 1129947
Street Improvements | 982837 | 789902
Water Distribution | 399800 | 340045
Oakland St. (Oliver Ave to Hawthorne Ave) | 1087994 | 800154.95 | Current Phase | Construction
Street Improvements | 737994 | 557379.95
Water Distribution | 350000 | 242775 | Sum of Bid Amount
Highway 30 Sanitary Sewer Relocation | 400000 | 322189.3 | 9539528
Sanitary Sewer System | 400000 | 322189.3
E. 14th St. (Glendale to Meadowlane) Meadowlane (E. 13th St. to E. 14th St.) | 380000 | 314426
Water Distribution | 380000 | 314426
Grand Total | 12424404 | 9861717.3

## Current Close-Out Projects
Current Phase | Close-Out | [6 empty] | Current Phase | (Multiple Items)
Program(s) Per Project | Sum of Overall Budget | Sum of Actual PSA Spent | Sum of Engineer's Est | Sum of Bid Amount | Sum of Final Construction Costs | Sum of Estimated COA Engineering / Admin |  | Row Labels | Count of Project Name
Kellogg Ave (7th St. to 13th St) 11th St (Burnett Ave to Kellogg Ave) | 808389.46 | 0 | 910652.5 | 808389.46 | 890901.93 | 122000 | What was previously allocated for 2023/24? | Sanitary Sewer System | 3
Northridge Heights Pond on GW Carver | 130091 | 24908.3 | 84980 | 111600 |  | 35000 |  | Stormwater | 4
S 500th Avenue County Line Road | 654121 | 0 | 702275 | 551057.7 | 542759.2 | 135000 |  | Street Improvements | 13
Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | 200000 | 0 | 231475 | 381800 |  | 0 |  | Water Distribution | 6
ROW Restoration |  | 0 |  |  |  | 22857 |  | Grand Total | 26
E 13th St (S. Dayton Ave to East of I-35) | 2300000 | 98700 | 2833264.5 | 2125500 | 2282092.96 | 0
Grand Total | 4092601.46 | 123608.3 | 4762647 | 3978347.16 | 3715754.09 | 314857
[8 empty] | Current Phase | Construction
Sum of Bid Amount
9539528

## Current Design Projects
Current Phase | Design |  | Current Phase | Design
Row Labels | Sum of Overall Budget | Sum of Engineer's Est | Row Labels | Count of Project Name
6th St / Duff Ave 20th St / Northwestern Ave S Bell Ave / SE 16th St Grove Ave / River Oak Dr | 500000 |  | Sanitary Sewer System | 12
No | 500000 |  | Shared Use Paths | 1
Alley south of Lincoln Way (S. Kellogg Ave to Sherman Ave) | 400000 | 160000 | Stormwater | 10
No | 400000 | 160000 | Street Improvements | 9
Basin 11 | 2100000 |  | Street Rehabilitation | 1
No | 2100000 |  | Water Distribution | 6
Bloomington Road (GW Carver to Eisenhower Ave) | 1300000 | 1057386.5 | Grand Total | 39
Yes | 1300000 | 1057386.5
Clear Creek bank Stabilization (west of Brittish Columbia Ave) | 249100
No | 249100
Clear Creek Bank Stablization (west of North Dakota Ave) | 350000
No | 350000
Douglas Ave (16th St to 17th St) Barr Drive 17th St (Douglas Ave to West St) | 1200000
No | 1200000
Downtown (Basin 12) | 2336322
No | 2336322
East/West alley north of Lincoln Way (Sherman Ave to Kellogg Ave) | 250000 | 180000
(blank) | 250000 | 180000
Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | 4390000 | 3677000
Yes | 4390000 | 3677000
South Skunk River (various locations between South East 16th Street and East Lincoln Way) | 654000
Yes | 654000 |  | Current Phase | Design
Stormwater System Analysis | 642257
No | 642257 |  | Sum of Overall Budget
Ferndale Ave (20th St to 24th St) Furman Drive | 1830000 | 2802834 | 31885597
No | 1830000 | 2802834
East Lincoln Way & Nikkol Trunk Line | 7500000
No | 7500000
Worrell Creek Bank Stabilization (south of Mortensen Pkwy from Gateway Hill Park Dr to University Blvd) | 850000 | 670000
Yes | 850000 | 670000
Grand & 13th Intersection | 758000 | 758000
(blank) | 758000 | 758000
Sunset Drive (Ash Ave to Beach Ave) | 1805000 | 1652812.13
Yes | 1100000 | 958272.13
(blank) | 705000 | 694540
US 69 (Basin 12) | 725918
(blank) | 725918
Moore Memorial Park Sanitary Sewer Lining | 0 | 148640
(blank) | 0 | 148640
Inis Grove (near restroom) | 600000
No | 600000
Animal Shelter Site | 100000
(blank) | 100000
Campus Ave (Lincoln Way to Oakland St) | 1530000 | 1033567.75
Yes | 1530000 | 1033567.75
Clark Ave (9th St to 13th St) | 1815000 | 1648991.6
Yes | 565000 | 563875
(blank) | 1250000 | 1085116.6
Grand Total | 31885597 | 13789231.98

## Water Improvements Fund
Current Phase | (Multiple Items) |  | Fund | Account | 10/02/2025 Account Balances
Fund Name | Water Utility |  | 510-Water Utility Fund | 510-8461-489 | 2246062
Account/Location | Sum of Overall Budget | Sum of Engineer's Est | Sum of Bid Amount | Sum of Final Construction Costs | Sum of Anticipated Costs Unincombered
510-8401-489 | 399800 | 251815 | 340045
Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | 399800 | 251815 | 340045
63042 | 399800 | 251815 | 340045
510-8461-489 | 3038389.46 | 1741302.5 | 1051164.46 | 890901.93
Douglas Ave (16th St to 17th St) Barr Drive 17th St (Douglas Ave to West St) | 1200000
(blank) | 1200000
Kellogg Ave (7th St. to 13th St) 11th St (Burnett Ave to Kellogg Ave) | 808389.46 | 910652.5 | 808389.46 | 890901.93
63386 | 808389.46 | 910652.5 | 808389.46 | 890901.93
Ferndale Ave (20th St to 24th St) Furman Drive | 680000 | 587875
(blank) | 680000 | 587875
Oakland St. (Oliver Ave to Hawthorne Ave) | 350000 | 242775 | 242775
64739 | 350000 | 242775 | 242775
510-7525-489 | 690000 | 690000
Grand & 13th Intersection | 690000 | 690000
(blank) | 690000 | 690000
510-8118-489 | 230000 | 200000
Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | 230000 | 200000
(blank) | 230000 | 200000
510-8465-489 | 380000 | 330216 | 314426
E. 14th St. (Glendale to Meadowlane) Meadowlane (E. 13th St. to E. 14th St.) | 380000 | 330216 | 314426
64734 | 380000 | 330216 | 314426
510-8131-489 | 28000 | 39220 | 27430
6th St (Brookridge Ave to Northwestern Ave) | 28000 | 39220 | 27430
63041 | 28000 | 39220 | 27430
510-8161-489 | 340000 | 333490
Sunset Drive (Ash Ave to Beach Ave) | 340000 | 333490
(blank) | 340000 | 333490
510-8159-489 | 512000 | 511375
Clark Ave (9th St to 13th St) | 512000 | 511375
(blank) | 512000 | 511375
Grand Total | 5618189.46 | 4097418.5 | 1733065.46 | 890901.93

## Sanitary Sewer Fund
Current Phase | (Multiple Items) |  |  | Fund | Account | 9/3/2025 balance | Notes
Fund Name | (Multiple Items) |  |  | 520-Sanitary Sewer Fund | 520-8542-489 | 616514 | Remaining after Encombered
Row Labels | Sum of Overall Budget | Sum of Engineer's Est | Sum of Bid Amount | Sum of Final Construction Costs | Sum of Anticipated Costs Unincombered
520-8501-489 | 200000 | 231475 | 381800 |  | 12000
Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | 200000 | 231475 | 381800 |  | 12000
63042 | 200000 | 231475 | 381800 |  | 12000
520-8542-489 | 20500 | 169140 | 20500
Hyland Ave (Lincoln Way to Ontario St) | 20500 | 20500 | 20500
64389 | 20500 | 20500 | 20500
East Lincoln Way & Nikkol Trunk Line
(blank)
Moore Memorial Park Sanitary Sewer Lining | 0 | 148640
(blank) | 0 | 148640
522-8551-489 | 2100000
Basin 11 | 2100000
(blank) | 2100000
522-8552-489 | 725918
US 69 (Basin 12) | 725918
(blank) | 725918
522-8553-489 | 2336322
Downtown (Basin 12) | 2336322
(blank) | 2336322
522-8554-489 | 7500000
East Lincoln Way & Nikkol Trunk Line | 7500000
(blank) | 7500000
520-7525-489 | 68000 | 68000
Grand & 13th Intersection | 68000 | 68000
(blank) | 68000 | 68000
520-8160-489 | 80000 | 69900
Campus Ave (Lincoln Way to Oakland St) | 80000 | 69900
(blank) | 80000 | 69900
520-8118-489 | 100000 | 80000
Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | 100000 | 80000
(blank) | 100000 | 80000
520-8521-489 | 400000 | 350000 | 322189.3
Highway 30 Sanitary Sewer Relocation | 400000 | 350000 | 322189.3
(blank) | 400000 | 350000 | 322189.3
520-8131-489 | 35000 | 35500 | 35000
6th St (Brookridge Ave to Northwestern Ave) | 35000 | 35500 | 35000
63041 | 35000 | 35500 | 35000
520-8161-489 | 95000 | 93000
Sunset Drive (Ash Ave to Beach Ave) | 95000 | 93000
(blank) | 95000 | 93000
520-8159-489 | 53000 | 52500
Clark Ave (9th St to 13th St) | 53000 | 52500
(blank) | 53000 | 52500
Grand Total | 13713740 | 1149515 | 759489.3 |  | 12000
604514

## ARPA Fund
Current Phase | (Multiple Items) |  |  | Fund | Account | 4/1/2025 Account Balances | Notes
Fund Name | American Rescue Plan | [5 empty] | Remaining after Encombered
Row Labels | Sum of Overall Budget | Sum of Engineer's Est | Sum of Bid Amount | Sum of Final Construction Costs
122-8573-489 | 654121 | 702275 | 551057.7 | 542759.2
S 500th Avenue County Line Road | 654121 | 702275 | 551057.7 | 542759.2
63957 | 654121 | 702275 | 551057.7 | 542759.2
122-8520-489 | 2300000 | 2833264.5 | 2125500 | 2282092.96
E 13th St (S. Dayton Ave to East of I-35) | 2300000 | 2833264.5 | 2125500 | 2282092.96
62500 | 2300000 | 2833264.5 | 2125500 | 2282092.96
Grand Total | 2954121 | 3535539.5 | 2676557.7 | 2824852.16

## Stormwater Fund
Current Phase | (Multiple Items) |  |  | Fund | Account | 8/12/2025 Account Balances | Notes | Fund | Account | 4/1/2025 Account Balances | Notes
Fund Name | (Multiple Items) |  |  | 560 | 560-8642-439 | 1284402 | Remaining after Encombered | 560 | 560-8601-439 | 173477 | Remaining after Encombered
Row Labels | Sum of Overall Budget | Sum of Engineer's Est | Sum of Bid Amount | Sum of Final Construction Costs | Sum of Anticipated Costs Unincombered
560-8601-489 | 100000 | [8 empty] | 100000 | Original Budget
Animal Shelter Site | 100000
(blank) | 100000
560-8605-489 | 642257
Stormwater System Analysis | 642257
(blank) | 642257
560-8626-489 | 130091 | 84980 | 111600 |  | 35000
Northridge Heights Pond on GW Carver | 130091 | 84980 | 111600 |  | 35000
63112 | 130091 | 84980 | 111600 |  | 35000
560-8635-489 | 654000
South Skunk River (various locations between South East 16th Street and East Lincoln Way) | 654000
(blank) | 654000
560-8636-489 | 1258000 | 958953 | 787433
Ioway Creek (6th St. to 13th St) | 1258000 | 958953 | 787433
64278 | 1258000 | 958953 | 787433
560-8638-489 | 249100
Clear Creek bank Stabilization (west of Brittish Columbia Ave) | 249100
(blank) | 249100
560-8639-489 | 600000
Inis Grove (near restroom) | 600000
(blank) | 600000
560-8640-489 | 350000
Clear Creek Bank Stablization (west of North Dakota Ave) | 350000
(blank) | 350000
560-8659-489 | 1132146 | 518000 | 523245.2
1100 Kennedy St East Lincoln Way (2000 block) 2100/2200 Jensen Ave Barr Drive Pearle Ave Alley Harrison Road (1900 block) Northridge Lane (2800 block) Garnet Dr (700 block) Idaho Ct (1200 block) | 632146 | 518000 | 523245.2
64556 | 632146 | 518000 | 523245.2
6th St / Duff Ave 20th St / Northwestern Ave S Bell Ave / SE 16th St Grove Ave / River Oak Dr | 500000
(blank) | 500000
561-8636-489 | 900000 | 900000 | 900000 | 900000 | 0
Ioway Creek (6th St. to 13th St) | 900000 | 900000 | 900000 | 900000 | 0
64278 | 900000 | 900000 | 900000 | 900000 | 0
560-8194-439
ROW Restoration
(blank)
560-8183-489 | 250000 | 210731.5 | 196124
S. 16th (University Boulevard to Apple Place) | 250000 | 210731.5 | 196124
(blank) | 250000 | 210731.5 | 196124
560-8634-489 | 850000 | 670000
Worrell Creek Bank Stabilization (south of Mortensen Pkwy from Gateway Hill Park Dr to University Blvd) | 850000 | 670000
(blank) | 850000 | 670000
560-8118-489 | 60000 | 57000
Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | 60000 | 57000
(blank) | 60000 | 57000
560-8161-489 | 270000 | 268050
Sunset Drive (Ash Ave to Beach Ave) | 270000 | 268050
(blank) | 270000 | 268050
Grand Total | 7445594 | 3667714.5 | 2518402.2 | 900000 | 35000
1284402

## Street Improvements
Current Phase | (Multiple Items) |  |  | Fund | Account | 8/5/2025 Account Balances | Notes
Fund Name | (Multiple Items) |  |  | Unallocated Funds | 20/21, 21/22, 22/23 GO Bonds and project savings | 923188
Row Labels | Sum of Overall Budget | Sum of Engineer's Est | Sum of Bid Amount | Sum of Final Construction Costs
060-7770-439 | 150000 | 330959
Ferndale Ave (20th St to 24th St) Furman Drive | 150000 | 330959
(blank) | 150000 | 330959
060-8131-489 | 75000 | 75000 | 75000 | 75000
6th St (Brookridge Ave to Northwestern Ave) | 75000 | 75000 | 75000 | 75000
63041 | 75000 | 75000 | 75000 | 75000
320-8184-439 | 1890000 | 1747800 | 1260304.05
Hyland Ave (Lincoln Way to Ontario St) | 1890000 | 1747800 | 1260304.05
64389 | 1890000 | 1747800 | 1260304.05
380-8184-439 | 220890 | 220890 | 220890
Hyland Ave (Lincoln Way to Ontario St) | 220890 | 220890 | 220890
64389 | 220890 | 220890 | 220890
381-8132-439 | 193790 | 193790 | 193790
Oakland St. (Oliver Ave to Hawthorne Ave) | 193790 | 193790 | 193790
64739 | 193790 | 193790 | 193790
381-8184-439 | 510000 | 510000 | 510000
Hyland Ave (Lincoln Way to Ontario St) | 510000 | 510000 | 510000
64389 | 510000 | 510000 | 510000
382-8132-439 | 419675 | 261297.95 | 227054.95
Oakland St. (Oliver Ave to Hawthorne Ave) | 419675 | 261297.95 | 227054.95
64739 | 419675 | 261297.95 | 227054.95
383-8132-439 | 124529 | 136535 | 136535
Oakland St. (Oliver Ave to Hawthorne Ave) | 124529 | 136535 | 136535
64739 | 124529 | 136535 | 136535
383-8183-439 | 463298 | 463298 | 463298
S. 16th (University Boulevard to Apple Place) | 463298 | 463298 | 463298
(blank) | 463298 | 463298 | 463298
384-8131-439 | 1170300 | 1141766.18 | 1003926
6th St (Brookridge Ave to Northwestern Ave) | 1170300 | 1141766.18 | 1003926
63041 | 1170300 | 1141766.18 | 1003926
384-8183-439 | 220639 | 108504.1 | 108504.1
S. 16th (University Boulevard to Apple Place) | 220639 | 108504.1 | 108504.1
(blank) | 220639 | 108504.1 | 108504.1
384-8191-439 | 982837 | 847792.4 | 789902
Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | 982837 | 847792.4 | 789902
63042 | 982837 | 847792.4 | 789902
380-8131-489 | 120000 | 120000 | 120000 | 54020
6th St (Brookridge Ave to Northwestern Ave) | 120000 | 120000 | 120000 | 54020
63041 | 120000 | 120000 | 120000 | 54020
386-8133-439 | 500000 | 254015.5
Bloomington Road (GW Carver to Eisenhower Ave) | 500000 | 254015.5
(blank) | 500000 | 254015.5
386-8160-439 | 1450000 | 963667.75
Campus Ave (Lincoln Way to Oakland St) | 1450000 | 963667.75
(blank) | 1450000 | 963667.75
386-8101-489 | 1000000 | 1884000
Ferndale Ave (20th St to 24th St) Furman Drive | 1000000 | 1884000
(blank) | 1000000 | 1884000
383-8150-439 | 250000 | 180000
East/West alley north of Lincoln Way (Sherman Ave to Kellogg Ave) | 250000 | 180000
(blank) | 250000 | 180000
386-8118-489 | 4000000 | 3340000
Hillcrest Ave Ellis Street Kentucky Ave Illinois Ave Indiana Ave Oklahoma Dr Delaware Ave (N Dakota Ave to Ontario St) | 4000000 | 3340000
(blank) | 4000000 | 3340000
386-8161-439 | 1100000 | 958272.13
Sunset Drive (Ash Ave to Beach Ave) | 1100000 | 958272.13
(blank) | 1100000 | 958272.13
320-8133-439 | 700000 | 700000
Bloomington Road (GW Carver to Eisenhower Ave) | 700000 | 700000
(blank) | 700000 | 700000
386-8172-439 | 400000 | 160000
Alley south of Lincoln Way (S. Kellogg Ave to Sherman Ave) | 400000 | 160000
(blank) | 400000 | 160000
386-8159-439 | 1250000 | 1085116.6
Clark Ave (9th St to 13th St) | 1250000 | 1085116.6
(blank) | 1250000 | 1085116.6
Grand Total | 17190958 | 15682704.61 | 5109204.1 | 129020
923188

## Bid to Const Cost Comparison
Current Phase | (Multiple Items)
Row Labels | Sum of Bid Amount | Sum of Final Construction Costs | Sum of Percent Over/Under
2017/18 | 1440778 | 1409307.8 | 97.82%
Siphon Rehab (7 locations) | 1440778 | 1409307.8 | 97.82%
2018/19 | 194388.1 | 160643 | 82.64%
Airport Rd (from University Blvd to S. Riverside Dr.) | 194388.1 | 160643 | 82.64%
2019/20 | 2855053.15 | 2398243.2 | 84%
Basin 10 (Clark Ave to Maxwell Ave) | 1283163.75 | 814323.71 | 63.46%
Center Ave (from Lincoln Way to E 2nd St) Des Moines Ave (from Lincoln Way to E 3rd St) Douglas Ave (from 7th to 10th) E 2nd Street (from Duff Ave. to Center Ave) E 3rd Street (from Duff Ave to E. of Des Moines St) | 1571889.4 | 1583919.49 | 100.8%
2020/21 | 12214282.77 | 15389907.9 | 126%
8th St (Northwestern Ave to Duff Ave) | 1256246.21 | 1284528.26 | 102.3%
Baker Street | 1317872.65 | 1401355.78 | 106.3%
E 13th Street (Duff Ave to Meadowlane Ave) | 2934292.9 | 2878865.03 | 98.11%
E 20th Street (Duff Ave to Meadowlane Ave) | 776718.91 | 743263.53 | 95.69%
East Lincoln Way (Freel to Teller) | 5262486.1 | 8417881.3 | 160%
Ford St (Dayton Ave to Bell Ave) Bell Ave (E Lincoln Way to Ford Street) S. 17th St (West of Golden Aspen Dr to S. Kellogg Ave.) South Kellogg Ave ( S. 17th to S. 16th St) | 666666 | 664014 | 99.6%
2021/22 | 24913372.66 | 24130984.8373 | 96.86%
24th St (PineHurst Dr to Hayes Ave) Stange Ave (Blankenburg Dr. to 24th St.) | 4252314.23 | 4254540.83 | 100.1%
Alley (Duff Ave. to Sherman Ave.) | 127952 | 128224.62 | 100.2%
Ames High School & Veenker Golf | 3791558.69 | 3472507.52 | 91.59%
Bloomington Waterway (Hyde Ave to Harrison Road) | 206340 | 176305.2 | 85.44%
Harcourt Dr (from Garnet Dr to Jewel Dr) Opal Circle (from Opal Dr to east end) Opal Dr (Jewel Dr to Crystal St) Top-O-Hollow Rd (Bloomington Rd to Dawes Dr.) Turquoise Circle (Onyx St to S. End) | 2133380.02 | 2004436.7073 | 93.96%
Hoover Ave (24th St to Top-O-Hollow) | 2185487.58 | 2297135.21 | 105.1%
North 2nd St (N Elm Ave to N Maple Ave) South Kellogg Ave (South to Carroll Ave) | 995778.8 | 874041.48 | 87.77%
North Dakota Ave (from Ontario to UPRR) Ontario St (from North Dakota to Woodstock) | 1430118.6 | 1427992.7 | 99.85%
Northridge Heights Pond on GW Carver | 111600 |  | 0%
S Duff Ave (5th St. to Lincoln Way) | 2286813.8 | 2347765.51 | 102.7%
S. 16th (S Grand Ave to East of S Duff Ave) | 4114430.8 | 3811279.41 | 92.63%
Stafford Ave (13th St to Carroll Ave.) | 990785.14 | 988990.14 | 99.82%
US Hwy 69 Grand Ave (6th St to 12th St) Murray Dr (1400 block) SE 2nd St (S Duff-Sumner) 11th St (Grand - 150' east) | 2286813 | 2347765.51 | 102.7%
2022/23 | 15849549.17 | 15419162.8 | 97.28%
2400 S Duff Ave | 228269.5 | 227964.9 | 99.87%
28th St (Hoover Ave to Ferndale Ave) | 846926.84 | 867082.401 | 102.4%
9th St (Brookridge Ave to Northwestern Ave) Brookridge Ave (6th St to Ridgewood Ave) Alley (6th St to 9th St) Lee St (Brookridge Ave to Ridgewood Ave) Ridgewood Ave (6th St to 9th St) | 4203260.58 | 3446543.079 | 82%
Clear Creek Bank Stabilization (4921 Utah Dr) | 75615.4 | 61147.72 | 80.87%
E 13th St (S. Dayton Ave to East of I-35) | 2125500 | 2282092.96 | 107.4%
Lincoln Way (Beedle/Hickory Dr to Franklin Ave) | 3047987.2 | 2989186.52 | 98.07%
Murray Dr (Northwestern to Grand Ave) | 794593.95 | 786763.59 | 99.01%
N Sunset Ridge Sanitary Sewer | 941044.5 | 1215121.62 | 129.1%
North/South Alley (Adams Alley between Douglas Ave & Duff Ave) | 103062.3 | 103933.3 | 100.8%
Oakwood Rd (State Ave to University Ave) | 2034969.9 | 2098808.72 | 103.1%
Schubert St, Taft Ave, Wheeler St, and 20th St | 94500 | 91500 | 96.83%
US Highway 69 (Basin 12) | 1353819 | 1249017.99 | 92.26%
2023/24 | 8145518.35 | 8615799.43 | 105.8%
Airport Rd (from University Blvd to S. Riverside Dr.) | 1187598.89 | 1244526.13 | 104.8%
College Creek Bank Stabilization (Hemingway Drive) | 95143.17 | 114156.63 | 120%
Curtiss Ave (13th St to 16th St) Marston Ave (13th St to 16th St) Phoenix Circle Roosevelt Ave (13th St to 16th St) | 1566927.57 | 1809153.37 | 115.5%
E 7th St. (Crawford to End) North Riverside Dr (Lincoln Way to N 3rd) | 364298.7 | 788082.61 | 216.3%
East 16th St (Duff Ave to Maxwell Ave) Glendale Ave (E 13th St - E 16th St) Quebec St (4101 - Arizona Ave) Quebec Circle | 1828001.36 | 1656589.29 | 90.62%
Kellogg Ave (7th St. to 13th St) 11th St (Burnett Ave to Kellogg Ave) | 808389.46 | 890901.93 | 110.2%
N. Russell (N 2nd St to N 4th St) | 346858.5 | 377690.15 | 108.9%
Prairie View West: Prairie View East | 1015443 | 1191940.12 | 117.4%
S 500th Avenue County Line Road | 551057.7 | 542759.2 | 98.49%
Welch Ave (Chamberlain St to Knapp St) Chamberlain Place | 381800 |  | 0%
2024/25 | 2231591.5 | 345550.5 | 15.48%
550th (Ken Maril Rd to 265th St) | 2036000 | 167994 | 8.251%
Douglas Ave (14th to 16th) | 90681 | 72848 | 80.33%
East Lincoln Way (Teller Ave to Potter Ave) | 0 | 0 | #DIV/0!
Lincoln Way (Wilder Ave to County Line) |  |  | #DIV/0!
N. Russell (Lincoln Way to N 2nd St) | 104910.5 | 104708.5 | 99.81%
ROW Restoration |  |  | #DIV/0!
US Highway 69 (Ken Maril Rd to South Past Waterway) |  |  | #DIV/0!
2025/26 | 49942.46 | 49942.46 | 100%
25/26 Sanitary and Storm Televising | 49942.46 | 49942.46 | 100%
Grand Total | 67894476.16 | 67919541.9273 | 100%

## Code Lookup
Fund |  | Department |  | Division | Program |  | Element/Object
30 | Local Option Sales Tax | 80 | Public Works Engineering |  | 419 | General Government CIP | 7501 | Land
60 | Road Use Tax | 81 | Street Engineering CIP |  | 429 | Public Safety CIP | 7502 | Right-of-Way
87 | CDBG | 82 | Utility Maintenance |  | 431 | Street System | 7503 | Easements
122 | American Rescue Plan | 83 | Utilit Locating |  | 432 | Street Lighting | 7511 | Buildings/Sructures
310 | Special Assessments | 84 | Water Distribution CIP |  | 434 | Public Parking | 7514 | Utility/Drainage Systems
320 | Street Construction | 85 | Sanitary Sewer CIP |  | 438 | Airport | 7517 | Streets/Transportation Network
330 | Airport Construction | 86 | Storm Water CIP |  | 469 | Community Development CIP | 7519 | Traffic Signals/Signs
340 | Park Developmnet | 87 | Storm Water Permit |  | 471 | GO Bond Debt Service | 7520 | Other Improvements
344 | Council Priority Projects |  |  |  | 472 | Electric Revenue Bonds
380 | 2019/20 GO Bonds |  |  |  | 474 | SRF Debt Service
381 | 2020/21 GO Bonds |  |  |  | 478 | Bond Cost
382 | 2021/22 GO Bonds |  |  |  | 482 | Water Utility
383 | 2022/23 GO Bonds |  |  |  | 483 | Stormwater Utility
384 | 2023/24 GO Bonds |  |  |  | 484 | Sewer Utility
385 | 2024/25 GO Bonds |  |  |  | 485 | Electric Services
386 | 2025/26 GO Bonds |  |  |  | 486 | Utility Customer Servie
387 | 2026/27 GO Bonds |  |  |  | 489 | Utilities CIP
388 | 2027/28 GO Bonds
389 | 2028/29 GO Bonds
390 | 2029/30 GO Bonds
391 | 2030/31 GO Bonds
392 | 2031/32 GO Bonds
393 | 2032/33 GO Bonds
394 | 2033/34 GO Bonds
510 | Water Utility
512 | Water Construction
520 | Sewer Utility
522 | Sewer Improvements (SRF)
530 | Electric Services
550 | Transit
551 | Transit/Student Government Trust
552 | Transit Capital Reserve
560 | Stormwater Utility
561 | Stormwater Improvements
Note, 522 (SRF Funds) will no longer be available after 2024
Note on J9: Bryngelson, Mindy: All costs associated with the acquisition of land.
Note on J10: Bryngelson, Mindy: All costs associated with acquisition of right-of-way.
Note on J11: Bryngelson, Mindy: All costs associated with acquisition of easements.
Note on J12: Bryngelson, Mindy: Construction and significant improvements to buildings and other major structures.
Note on J13: Bryngelson, Mindy: Costs associated with the development, construction, expansion, and replacement of the City’s utility and storm drainage systems. Used for Electric, Water, Sewer, and Storm Water Utility CIP projects.
Note on J14: Bryngelson, Mindy: Costs associated with the development, construction, expansion, and replacement of the City’s transportation network. Includes: Streets, Shared use paths, Alleys, Bridges, Sidewalks, Curb/gutter
Note on J15: Bryngelson, Mindy: Costs associated with the development, construction, expansion, and replacement of the City’s traffic signal network and major signage projects.
Note on J16: Bryngelson, Mindy: Capital improvements not otherwise classified. Examples includes: Park improvements, Golf course improvements, Parking lots, Airport runways, Public art, Security fencing